## Summary (35% AH)
Nestle Affordable Block Summary (35% AH)
| Phase | Start Date | GB Date | Practical Completion | S/O | A/R | Total
D1 | 2 | 2018-05-08 | 2018-08-30 | 2020-02-14 | 3 | 70 | 73
D2 | 2 | 2018-05-08 | 2018-08-15 | 2019-11-14 | 36 | 0 | 36
D3 | 2 | 2018-05-08 | 2018-08-01 | 2019-07-10 | 7 | 2 | 9
D4 | 2 | 2018-05-08 | 2018-09-13 | 2019-12-06 | 6 | 0 | 6
E1 | 3 | 2019-10-21 | 2020-04-02 | 2021-10-12 | 54 | 2 | 56
E2 | 3 | 2019-10-21 | 2020-02-17 | 2021-06-18 | 42 | 1 | 43
E3 | 3 | 2019-10-21 | 2020-04-29 | 2021-03-01 | 8 | 0 | 8
B1 | 4 | 2021-11-24 | 2022-02-02 | 2023-10-30 | 0 | 4 | 4
B2 | 4 | 2021-11-24 | 2022-01-19 | 2023-08-30 | 0 | 3 | 3
B3 | 4 | 2021-11-24 | 2021-12-15 | 2023-04-19 | 0 | 4 | 4
B4 | 4 | 2022-01-26 | 2021-12-08 | 2022-12-22 | 0 | 3 | 3
B5 | 4 | 2021-12-22 | 2021-12-22 | 2023-02-13 | 34 | 4 | 38
B6 | 4 | 2021-12-22 | 2022-01-12 | 2023-05-23 | 37 | 3 | 40
B7 | 4 | 2021-12-22 | 2022-01-26 | 2024-02-19 | 43 | 0 | 43
B8 | 4 | 2021-12-22 | 2022-02-09 | 2024-03-21 | 24 | 3 | 27
B9 | 4 | 2021-12-22 | 2022-02-16 | 2024-07-16 | 23 | 0 | 23
C1 | 5 | 2023-07-24 | 2023-11-14 | 2024-10-28 | 3 | 29 | 32
C2 | 5 | 2023-07-24 | 2023-12-12 | 2024-12-20 | 3 | 1 | 4
C3 | 5 | 2023-07-24 | 2024-01-09 | 2024-12-20 | 0 | 3 | 3
C4 | 5 | 2023-07-24 | 2024-01-16 | 2024-12-20 | 3 | 1 | 4
C5 | 5 | 2023-07-24 | 2023-11-28 | 2024-10-28 | 4 | 0 | 4
C6 | 5 | 2023-07-24 | 2023-12-12 | 2024-10-28 | 0 | 6 | 6
Total |  |  |  |  | 330 | 139 | 469
% |  |  |  |  | 70.36% | 29.64%

## Detailed Schedule (35% AH)
FORMER NESTLE FACTORY, HAYES
MAKOWER ARCHITECTS / HAWKINS BROWN / dMFK Accommodation Schedule
| 2017-04-05 | [5 empty] | Actual NSA |  |  | Shared Ownership | [15 empty] | Rented
| Flat No. | Level | Block | Type | Beds | Hab Rms | SQ M | SQ FT | Tenure | Studio | 1 Bed Flat | 1 Bed Duplex | 1 Bed House | 2 Bed Flat | 2 Bed Duplex | 2 Bed House | 3 Bed Flat | 3 Bed Duplex | 3 Bed House | 4 Bed Flat | 4 Bed Triplex | 4 Bed House | 5 Bed Flat | 5 Bed Duplex | 5 Bed House | Studio | 1 Bed Flat | 1 Bed Duplex | 1 Bed House | 2 Bed Flat | 2 Bed Duplex | 2 Bed House | 3 Bed Flat | 3 Bed Duplex | 3 Bed House | 4 Bed Flat | 4 Bed Triplex | 4 Bed House | 5 Bed Flat | 5 Bed Duplex | 5 Bed House
B1 | B1.00.01 | GF - 1st F | B1 | Duplex | 3 | 4 | 93.92 | 1010.9549 | Rented | [24 empty] | 1010.9549 | [7 empty] | 1010.9549 | 0
| B1.00.02 | GF - 1st F | B1 | Duplex | 3 | 4 | 93.89 | 1010.632 | Rented | [24 empty] | 1010.632 | [7 empty] | 1010.632 | 0
| B1.00.03 | GF - 1st F | B1 | Duplex | 3 | 4 | 93.91 | 1010.8472 | Rented | [24 empty] | 1010.8472 | [7 empty] | 1010.8472 | 0
| B1.00.04 | GF - 1st F | B1 | Duplex | 3 | 4 | 107.43 | 1156.3765 | Rented | [24 empty] | 1156.3765 | [7 empty] | 1156.3765 | 0
B2 | B2.01.01 | GF | B2 | Duplex | 3 | 4 | 93.91 | 1010.8472 | Rented | [24 empty] | 1010.8472 | [7 empty] | 1010.8472 | 0
| B2.01.02 | GF | B2 | Duplex | 3 | 4 | 93.89 | 1010.632 | Rented | [24 empty] | 1010.632 | [7 empty] | 1010.632 | 0
| B2.01.03 | GF | B2 | Duplex | 3 | 4 | 93.92 | 1010.9549 | Rented | [24 empty] | 1010.9549 | [7 empty] | 1010.9549 | 0
B3 | B3.00.02 | GF - 1st F | B3 | Duplex | 3 | 4 | 93.83 | 1009.9861 | Rented | [24 empty] | 1009.9861 | [7 empty] | 1009.9861 | 0
| B3.00.03 | GF - 1st F | B3 | Duplex | 3 | 4 | 93.87 | 1010.4167 | Rented | [24 empty] | 1010.4167 | [7 empty] | 1010.4167 | 0
| B3.00.04 | GF - 1st F | B3 | Duplex | 3 | 4 | 93.87 | 1010.4167 | Rented | [24 empty] | 1010.4167 | [7 empty] | 1010.4167 | 0
| B3.00.05 | GF - 1st F | B3 | Duplex | 3 | 4 | 93.92 | 1010.9549 | Rented | [24 empty] | 1010.9549 | [7 empty] | 1010.9549 | 0
B4 | B4.00.02 | GF - 1st F | B4 | Duplex | 3 | 4 | 93.59 | 1007.4028 | Rented | [24 empty] | 1007.4028 | [7 empty] | 1007.4028 | 0
| B4.00.03 | GF - 1st F | B4 | Duplex | 3 | 4 | 93.59 | 1007.4028 | Rented | [24 empty] | 1007.4028 | [7 empty] | 1007.4028 | 0
| B4.00.04 | GF - 1st F | B4 | Duplex | 3 | 4 | 93.59 | 1007.4028 | Rented | [24 empty] | 1007.4028 | [7 empty] | 1007.4028 | 0
B5 | B5.00.01 | Ground Floor | B5 | Flat | 2 | 3 | 68.51 | 737.4416 | S/O |  |  |  |  | 737.4416 | [27 empty] | 737.4416 | 0
| B5.00.02 | GF - 1st F | B5 | Duplex | 3 | 4 | 93.8 | 1009.6632 | Rented | [24 empty] | 1009.6632 | [7 empty] | 1009.6632 | 0
| B5.00.03 | GF - 1st F | B5 | Duplex | 3 | 4 | 93.87 | 1010.4167 | Rented | [24 empty] | 1010.4167 | [7 empty] | 1010.4167 | 0
| B5.00.04 | GF - 1st F | B5 | Duplex | 3 | 4 | 93.87 | 1010.4167 | Rented | [24 empty] | 1010.4167 | [7 empty] | 1010.4167 | 0
| B5.00.05 | GF - 1st F | B5 | Duplex | 3 | 4 | 91.59 | 985.8748 | Rented | [24 empty] | 985.8748 | [7 empty] | 985.8748 | 0
| B5.01.06 | 1st Floor | B5 | Flat | 2 | 3 | 75.79 | 815.8036 | S/O |  |  |  |  | 815.8036 | [27 empty] | 815.8036 | 0
| B5.02.07 | 2nd Floor | B5 | Flat | 1 | 2 | 50.78 | 546.5959 | S/O |  | 546.5959 | [30 empty] | 546.5959 | 0
| B5.02.08 | 2nd Floor | B5 | Flat | 1 | 2 | 50.1 | 539.2764 | S/O |  | 539.2764 | [30 empty] | 539.2764 | 0
| B5.02.09 | 2nd Floor | B5 | Flat | 2 | 3 | 69.14 | 744.223 | S/O |  |  |  |  | 744.223 | [27 empty] | 744.223 | 0
| B5.02.10 | 2nd Floor | B5 | Flat | 2 | 3 | 68.67 | 739.1639 | S/O |  |  |  |  | 739.1639 | [27 empty] | 739.1639 | 0
| B5.02.11 | 2nd Floor | B5 | Flat | 1 | 2 | 51 | 548.964 | S/O |  | 548.964 | [30 empty] | 548.964 | 0
| B5.02.12 | 2nd Floor | B5 | Flat | 2 | 3 | 68.81 | 740.6708 | S/O |  |  |  |  | 740.6708 | [27 empty] | 740.6708 | 0
| B5.02.13 | 2nd Floor | B5 | Flat | 1 | 2 | 50.66 | 545.3042 | S/O |  | 545.3042 | [30 empty] | 545.3042 | 0
| B5.02.14 | 2nd Floor | B5 | Flat | 1 | 2 | 50.78 | 546.5959 | S/O |  | 546.5959 | [30 empty] | 546.5959 | 0
| B5.03.15 | 3rd Floor | B5 | Flat | 1 | 2 | 50.78 | 546.5959 | S/O |  | 546.5959 | [30 empty] | 546.5959 | 0
| B5.03.16 | 3rd Floor | B5 | Flat | 1 | 2 | 50.1 | 539.2764 | S/O |  | 539.2764 | [30 empty] | 539.2764 | 0
| B5.03.17 | 3rd Floor | B5 | Flat | 2 | 3 | 69.14 | 744.223 | S/O |  |  |  |  | 744.223 | [27 empty] | 744.223 | 0
| B5.03.18 | 3rd Floor | B5 | Flat | 2 | 3 | 68.67 | 739.1639 | S/O |  |  |  |  | 739.1639 | [27 empty] | 739.1639 | 0
| B5.03.19 | 3rd Floor | B5 | Flat | 1 | 2 | 51 | 548.964 | S/O |  | 548.964 | [30 empty] | 548.964 | 0
| B5.03.20 | 3rd Floor | B5 | Flat | 2 | 3 | 68.81 | 740.6708 | S/O |  |  |  |  | 740.6708 | [27 empty] | 740.6708 | 0
| B5.03.21 | 3rd Floor | B5 | Flat | 1 | 2 | 50.66 | 545.3042 | S/O |  | 545.3042 | [30 empty] | 545.3042 | 0
| B5.03.22 | 3rd Floor | B5 | Flat | 1 | 2 | 50.78 | 546.5959 | S/O |  | 546.5959 | [30 empty] | 546.5959 | 0
| B5.04.23 | 4th Floor | B5 | Flat | 1 | 2 | 50.78 | 546.5959 | S/O |  | 546.5959 | [30 empty] | 546.5959 | 0
| B5.04.24 | 4th Floor | B5 | Flat | 1 | 2 | 50.1 | 539.2764 | S/O |  | 539.2764 | [30 empty] | 539.2764 | 0
| B5.04.25 | 4th Floor | B5 | Flat | 2 | 3 | 69.14 | 744.223 | S/O |  |  |  |  | 744.223 | [27 empty] | 744.223 | 0
| B5.04.26 | 4th Floor | B5 | Flat | 2 | 3 | 68.67 | 739.1639 | S/O |  |  |  |  | 739.1639 | [27 empty] | 739.1639 | 0
| B5.04.27 | 4th Floor | B5 | Flat | 1 | 2 | 51 | 548.964 | S/O |  | 548.964 | [30 empty] | 548.964 | 0
| B5.04.28 | 4th Floor | B5 | Flat | 2 | 3 | 68.81 | 740.6708 | S/O |  |  |  |  | 740.6708 | [27 empty] | 740.6708 | 0
| B5.04.29 | 4th Floor | B5 | Flat | 1 | 2 | 50.66 | 545.3042 | S/O |  | 545.3042 | [30 empty] | 545.3042 | 0
| B5.04.30 | 4th Floor | B5 | Flat | 1 | 2 | 50.78 | 546.5959 | S/O |  | 546.5959 | [30 empty] | 546.5959 | 0
| B5.05.31 | 5th Floor | B5 | Flat | 1 | 2 | 50.78 | 546.5959 | S/O |  | 546.5959 | [30 empty] | 546.5959 | 0
| B5.05.32 | 5th Floor | B5 | Flat | 1 | 2 | 50.1 | 539.2764 | S/O |  | 539.2764 | [30 empty] | 539.2764 | 0
| B5.05.33 | 5th Floor | B5 | Flat | 2 | 3 | 69.14 | 744.223 | S/O |  |  |  |  | 744.223 | [27 empty] | 744.223 | 0
| B5.05.34 | 5th Floor | B5 | Flat | 2 | 3 | 68.67 | 739.1639 | S/O |  |  |  |  | 739.1639 | [27 empty] | 739.1639 | 0
| B5.05.35 | 5th Floor | B5 | Flat | 1 | 2 | 51 | 548.964 | S/O |  | 548.964 | [30 empty] | 548.964 | 0
| B5.05.36 | 5th Floor | B5 | Flat | 2 | 3 | 68.81 | 740.6708 | S/O |  |  |  |  | 740.6708 | [27 empty] | 740.6708 | 0
| B5.05.37 | 5th Floor | B5 | Flat | 1 | 2 | 50.66 | 545.3042 | S/O |  | 545.3042 | [30 empty] | 545.3042 | 0
| B5.05.38 | 5th Floor | B5 | Flat | 1 | 2 | 50.78 | 546.5959 | S/O |  | 546.5959 | [30 empty] | 546.5959 | 0
B6 | B6.00.01 | GF - 1st F | B6 | Duplex | 3 | 4 | 93.92 | 1010.9549 | Rented | [24 empty] | 1010.9549 | [7 empty] | 1010.9549 | 0
| B6.00.02 | GF - 1st F | B6 | Duplex | 3 | 4 | 93.87 | 1010.4167 | Rented | [24 empty] | 1010.4167 | [7 empty] | 1010.4167 | 0
| B6.00.03 | GF - 1st F | B6 | Duplex | 3 | 4 | 93.87 | 1010.4167 | Rented | [24 empty] | 1010.4167 | [7 empty] | 1010.4167 | 0
| B6.01.04 | 1st Floor | B6 | Flat | 2 | 3 | 68.41 | 736.3652 | S/O |  |  |  |  | 736.3652 | [27 empty] | 736.3652 | 0
| B6.01.05 | 1st Floor | B6 | Flat | 2 | 3 | 74.63 | 803.3173 | S/O |  |  |  |  | 803.3173 | [27 empty] | 803.3173 | 0
| B6.02.06 | 2nd Floor | B6 | Flat | 1 | 2 | 50.78 | 546.5959 | S/O |  | 546.5959 | [30 empty] | 546.5959 | 0
| B6.02.07 | 2nd Floor | B6 | Flat | 1 | 2 | 50.58 | 544.4431 | S/O |  | 544.4431 | [30 empty] | 544.4431 | 0
| B6.02.08 | 2nd Floor | B6 | Flat | 2 | 3 | 64.54 | 694.7086 | S/O |  |  |  |  | 694.7086 | [27 empty] | 694.7086 | 0
| B6.02.09 | 2nd Floor | B6 | Flat | 2 | 3 | 68.67 | 739.1639 | S/O |  |  |  |  | 739.1639 | [27 empty] | 739.1639 | 0
| B6.02.10 | 2nd Floor | B6 | Flat | 1 | 2 | 51 | 548.964 | S/O |  | 548.964 | [30 empty] | 548.964 | 0
| B6.02.11 | 2nd Floor | B6 | Flat | 2 | 3 | 69.14 | 744.223 | S/O |  |  |  |  | 744.223 | [27 empty] | 744.223 | 0
| B6.02.12 | 2nd Floor | B6 | Flat | 1 | 2 | 50.76 | 546.3806 | S/O |  | 546.3806 | [30 empty] | 546.3806 | 0
| B6.02.13 | 2nd Floor | B6 | Flat | 1 | 2 | 50.78 | 546.5959 | S/O |  | 546.5959 | [30 empty] | 546.5959 | 0
| B6.03.14 | 3rd Floor | B6 | Flat | 1 | 2 | 50.78 | 546.5959 | S/O |  | 546.5959 | [30 empty] | 546.5959 | 0
| B6.03.15 | 3rd Floor | B6 | Flat | 2 | 3 | 74.57 | 802.6715 | S/O |  |  |  |  | 802.6715 | [27 empty] | 802.6715 | 0
| B6.03.16 | 3rd Floor | B6 | Flat | 2 | 3 | 77.33 | 832.3801 | S/O |  |  |  |  | 832.3801 | [27 empty] | 832.3801 | 0
| B6.03.17 | 3rd Floor | B6 | Flat | 0 | 1 | 39.45 | 424.6398 | S/O | 424.6398 | [31 empty] | 424.6398 | 0
| B6.03.18 | 3rd Floor | B6 | Flat | 1 | 2 | 51 | 548.964 | S/O |  | 548.964 | [30 empty] | 548.964 | 0
| B6.03.19 | 3rd Floor | B6 | Flat | 1 | 2 | 51 | 548.964 | S/O |  | 548.964 | [30 empty] | 548.964 | 0
| B6.03.20 | 3rd Floor | B6 | Flat | 2 | 3 | 69.14 | 744.223 | S/O |  |  |  |  | 744.223 | [27 empty] | 744.223 | 0
| B6.03.21 | 3rd Floor | B6 | Flat | 1 | 2 | 50.76 | 546.3806 | S/O |  | 546.3806 | [30 empty] | 546.3806 | 0
| B6.03.22 | 3rd Floor | B6 | Flat | 1 | 2 | 50.78 | 546.5959 | S/O |  | 546.5959 | [30 empty] | 546.5959 | 0
| B6.04.23 | 4th Floor | B6 | Flat | 1 | 2 | 50.78 | 546.5959 | S/O |  | 546.5959 | [30 empty] | 546.5959 | 0
| B6.04.24 | 4th Floor | B6 | Flat | 2 | 3 | 74.58 | 802.7791 | S/O |  |  |  |  | 802.7791 | [27 empty] | 802.7791 | 0
| B6.04.25 | 4th Floor | B6 | Flat | 2 | 3 | 77.33 | 832.3801 | S/O |  |  |  |  | 832.3801 | [27 empty] | 832.3801 | 0
| B6.04.26 | 4th Floor | B6 | Flat | 0 | 1 | 39.45 | 424.6398 | S/O | 424.6398 | [31 empty] | 424.6398 | 0
| B6.04.27 | 4th Floor | B6 | Flat | 1 | 2 | 51 | 548.964 | S/O |  | 548.964 | [30 empty] | 548.964 | 0
| B6.04.28 | 4th Floor | B6 | Flat | 1 | 2 | 51 | 548.964 | S/O |  | 548.964 | [30 empty] | 548.964 | 0
| B6.04.29 | 4th Floor | B6 | Flat | 2 | 3 | 69.14 | 744.223 | S/O |  |  |  |  | 744.223 | [27 empty] | 744.223 | 0
| B6.04.30 | 4th Floor | B6 | Flat | 1 | 2 | 50.76 | 546.3806 | S/O |  | 546.3806 | [30 empty] | 546.3806 | 0
| B6.04.31 | 4th Floor | B6 | Flat | 1 | 2 | 50.78 | 546.5959 | S/O |  | 546.5959 | [30 empty] | 546.5959 | 0
| B6.05.32 | 5th Floor | B6 | Flat | 1 | 2 | 50.78 | 546.5959 | S/O |  | 546.5959 | [30 empty] | 546.5959 | 0
| B6.05.33 | 5th Floor | B6 | Flat | 2 | 3 | 74.58 | 802.7791 | S/O |  |  |  |  | 802.7791 | [27 empty] | 802.7791 | 0
| B6.05.34 | 5th Floor | B6 | Flat | 2 | 3 | 77.33 | 832.3801 | S/O |  |  |  |  | 832.3801 | [27 empty] | 832.3801 | 0
| B6.05.35 | 5th Floor | B6 | Flat | 0 | 1 | 39.45 | 424.6398 | S/O | 424.6398 | [31 empty] | 424.6398 | 0
| B6.05.36 | 5th Floor | B6 | Flat | 1 | 2 | 51 | 548.964 | S/O |  | 548.964 | [30 empty] | 548.964 | 0
| B6.05.37 | 5th Floor | B6 | Flat | 1 | 2 | 51 | 548.964 | S/O |  | 548.964 | [30 empty] | 548.964 | 0
| B6.05.38 | 5th Floor | B6 | Flat | 2 | 3 | 69.14 | 744.223 | S/O |  |  |  |  | 744.223 | [27 empty] | 744.223 | 0
| B6.05.39 | 5th Floor | B6 | Flat | 1 | 2 | 50.76 | 546.3806 | S/O |  | 546.3806 | [30 empty] | 546.3806 | 0
| B6.05.40 | 5th Floor | B6 | Flat | 1 | 2 | 50.78 | 546.5959 | S/O |  | 546.5959 | [30 empty] | 546.5959 | 0
B7 | B7.00.01 | Ground Floor | B7 | Flat | 0 | 1 | 38.04 | 409.4626 | S/O | 409.4626 | [31 empty] | 409.4626 | 0
| B7.00.02 | Ground Floor | B7 | Flat | 2 | 3 | 72 | 775.008 | S/O |  |  |  |  | 775.008 | [27 empty] | 775.008 | 0
| B7.00.03 | Ground Floor | B7 | Flat | 0 | 1 | 37 | 398.268 | S/O | 398.268 | [31 empty] | 398.268 | 0
| B7.01.04 | 1st Floor | B7 | Flat | 0 | 1 | 37.27 | 401.1743 | S/O | 401.1743 | [31 empty] | 401.1743 | 0
| B7.01.05 | 1st Floor | B7 | Flat | 3 | 4 | 79.15 | 851.9706 | S/O | [7 empty] | 851.9706 | [24 empty] | 851.9706 | 0
| B7.01.06 | 1st Floor | B7 | Flat | 3 | 4 | 83.73 | 901.2697 | S/O | [7 empty] | 901.2697 | [24 empty] | 901.2697 | 0
| B7.01.07 | 1st Floor | B7 | Flat | 0 | 1 | 38.37 | 413.0147 | S/O | 413.0147 | [31 empty] | 413.0147 | 0
| B7.01.08 | 1st Floor | B7 | Flat | 2 | 3 | 74.96 | 806.8694 | S/O |  |  |  |  | 806.8694 | [27 empty] | 806.8694 | 0
| B7.01.09 | 1st Floor | B7 | Flat | 2 | 3 | 68.59 | 738.3028 | S/O |  |  |  |  | 738.3028 | [27 empty] | 738.3028 | 0
| B7.01.10 | 1st Floor | B7 | Flat | 2 | 3 | 74.76 | 804.7166 | S/O |  |  |  |  | 804.7166 | [27 empty] | 804.7166 | 0
| B7.02.11 | 2nd Floor | B7 | Flat | 0 | 1 | 37.27 | 401.1743 | S/O | 401.1743 | [31 empty] | 401.1743 | 0
| B7.02.12 | 2nd Floor | B7 | Flat | 3 | 4 | 79.16 | 852.0782 | S/O | [7 empty] | 852.0782 | [24 empty] | 852.0782 | 0
| B7.02.13 | 2nd Floor | B7 | Flat | 3 | 4 | 83.94 | 903.5302 | S/O | [7 empty] | 903.5302 | [24 empty] | 903.5302 | 0
| B7.02.14 | 2nd Floor | B7 | Flat | 0 | 1 | 38.37 | 413.0147 | S/O | 413.0147 | [31 empty] | 413.0147 | 0
| B7.02.15 | 2nd Floor | B7 | Flat | 1 | 2 | 51.16 | 550.6862 | S/O |  | 550.6862 | [30 empty] | 550.6862 | 0
| B7.02.16 | 2nd Floor | B7 | Flat | 1 | 2 | 51.16 | 550.6862 | S/O |  | 550.6862 | [30 empty] | 550.6862 | 0
| B7.02.17 | 2nd Floor | B7 | Flat | 2 | 3 | 68.96 | 742.2854 | S/O |  |  |  |  | 742.2854 | [27 empty] | 742.2854 | 0
| B7.02.18 | 2nd Floor | B7 | Flat | 2 | 3 | 67.43 | 725.8165 | S/O |  |  |  |  | 725.8165 | [27 empty] | 725.8165 | 0
| B7.02.19 | 2nd Floor | B7 | Flat | 0 | 1 | 37.27 | 401.1743 | S/O | 401.1743 | [31 empty] | 401.1743 | 0
| B7.03.20 | 3rd Floor | B7 | Flat | 0 | 1 | 37.27 | 401.1743 | S/O | 401.1743 | [31 empty] | 401.1743 | 0
| B7.03.21 | 3rd Floor | B7 | Flat | 2 | 3 | 67.52 | 726.7853 | S/O |  |  |  |  | 726.7853 | [27 empty] | 726.7853 | 0
| B7.03.22 | 3rd Floor | B7 | Flat | 2 | 3 | 68.98 | 742.5007 | S/O |  |  |  |  | 742.5007 | [27 empty] | 742.5007 | 0
| B7.03.23 | 3rd Floor | B7 | Flat | 1 | 2 | 51.16 | 550.6862 | S/O |  | 550.6862 | [30 empty] | 550.6862 | 0
| B7.03.24 | 3rd Floor | B7 | Flat | 1 | 2 | 51.16 | 550.6862 | S/O |  | 550.6862 | [30 empty] | 550.6862 | 0
| B7.03.25 | 3rd Floor | B7 | Flat | 2 | 3 | 68.96 | 742.2854 | S/O |  |  |  |  | 742.2854 | [27 empty] | 742.2854 | 0
| B7.03.26 | 3rd Floor | B7 | Flat | 2 | 3 | 67.43 | 725.8165 | S/O |  |  |  |  | 725.8165 | [27 empty] | 725.8165 | 0
| B7.03.27 | 3rd Floor | B7 | Flat | 0 | 1 | 37.27 | 401.1743 | S/O | 401.1743 | [31 empty] | 401.1743 | 0
| B7.04.28 | 4th Floor | B7 | Flat | 0 | 1 | 37.27 | 401.1743 | S/O | 401.1743 | [31 empty] | 401.1743 | 0
| B7.04.29 | 4th Floor | B7 | Flat | 2 | 3 | 67.52 | 726.7853 | S/O |  |  |  |  | 726.7853 | [27 empty] | 726.7853 | 0
| B7.04.30 | 4th Floor | B7 | Flat | 2 | 3 | 68.98 | 742.5007 | S/O |  |  |  |  | 742.5007 | [27 empty] | 742.5007 | 0
| B7.04.31 | 4th Floor | B7 | Flat | 1 | 2 | 51.16 | 550.6862 | S/O |  | 550.6862 | [30 empty] | 550.6862 | 0
| B7.04.32 | 4th Floor | B7 | Flat | 1 | 2 | 51.16 | 550.6862 | S/O |  | 550.6862 | [30 empty] | 550.6862 | 0
| B7.04.33 | 4th Floor | B7 | Flat | 2 | 3 | 68.96 | 742.2854 | S/O |  |  |  |  | 742.2854 | [27 empty] | 742.2854 | 0
| B7.04.34 | 4th Floor | B7 | Flat | 2 | 3 | 67.43 | 725.8165 | S/O |  |  |  |  | 725.8165 | [27 empty] | 725.8165 | 0
| B7.04.35 | 4th Floor | B7 | Flat | 0 | 1 | 37.27 | 401.1743 | S/O | 401.1743 | [31 empty] | 401.1743 | 0
| B7.05.36 | 5th Floor | B7 | Flat | 0 | 1 | 37.27 | 401.1743 | S/O | 401.1743 | [31 empty] | 401.1743 | 0
| B7.05.37 | 5th Floor | B7 | Flat | 2 | 3 | 67.52 | 726.7853 | S/O |  |  |  |  | 726.7853 | [27 empty] | 726.7853 | 0
| B7.05.38 | 5th Floor | B7 | Flat | 2 | 3 | 68.98 | 742.5007 | S/O |  |  |  |  | 742.5007 | [27 empty] | 742.5007 | 0
| B7.05.39 | 5th Floor | B7 | Flat | 1 | 2 | 51.16 | 550.6862 | S/O |  | 550.6862 | [30 empty] | 550.6862 | 0
| B7.05.40 | 5th Floor | B7 | Flat | 1 | 2 | 51.16 | 550.6862 | S/O |  | 550.6862 | [30 empty] | 550.6862 | 0
| B7.05.41 | 5th Floor | B7 | Flat | 2 | 3 | 68.96 | 742.2854 | S/O |  |  |  |  | 742.2854 | [27 empty] | 742.2854 | 0
| B7.05.42 | 5th Floor | B7 | Flat | 2 | 3 | 67.43 | 725.8165 | S/O |  |  |  |  | 725.8165 | [27 empty] | 725.8165 | 0
| B7.05.43 | 5th Floor | B7 | Flat | 0 | 1 | 37.27 | 401.1743 | S/O | 401.1743 | [31 empty] | 401.1743 | 0
B8 | B8.00.01 | Ground Floor | B8 | Flat | 1 | 2 | 50.41 | 542.6132 | S/O |  | 542.6132 | [30 empty] | 542.6132 | 0
| B8.00.02 | Ground Floor | B8 | Flat | 0 | 1 | 37.13 | 399.6673 | S/O | 399.6673 | [31 empty] | 399.6673 | 0
| B8.00.03 | GF - 1st F | B8 | Duplex | 3 | 4 | 93.55 | 1006.9722 | Rented | [24 empty] | 1006.9722 | [7 empty] | 1006.9722 | 0
| B8.00.04 | GF - 1st F | B8 | Duplex | 3 | 4 | 93.55 | 1006.9722 | Rented | [24 empty] | 1006.9722 | [7 empty] | 1006.9722 | 0
| B8.00.05 | GF - 1st F | B8 | Duplex | 3 | 4 | 93.55 | 1006.9722 | Rented | [24 empty] | 1006.9722 | [7 empty] | 1006.9722 | 0
| B8.01.06 | 1st Floor | B8 | Flat | 2 | 3 | 75.59 | 813.6508 | S/O |  |  |  |  | 813.6508 | [27 empty] | 813.6508 | 0
| B8.02.07 | 1st Floor | B8 | Flat | 1 | 2 | 50.54 | 544.0126 | S/O |  | 544.0126 | [30 empty] | 544.0126 | 0
| B8.02.08 | 2nd Floor | B8 | Flat | 2 | 3 | 75.76 | 815.4806 | S/O |  |  |  |  | 815.4806 | [27 empty] | 815.4806 | 0
| B8.02.09 | 2nd Floor | B8 | Flat | 3 | 4 | 75.52 | 812.8973 | S/O | [7 empty] | 812.8973 | [24 empty] | 812.8973 | 0
| B8.02.10 | 2nd Floor | B8 | Flat | 1 | 2 | 50.76 | 546.3806 | S/O |  | 546.3806 | [30 empty] | 546.3806 | 0
| B8.02.11 | 2nd Floor | B8 | Flat | 2 | 3 | 75.81 | 816.0188 | S/O |  |  |  |  | 816.0188 | [27 empty] | 816.0188 | 0
| B8.03.12 | 3rd Floor | B8 | Flat | 2 | 3 | 75.81 | 816.0188 | S/O |  |  |  |  | 816.0188 | [27 empty] | 816.0188 | 0
| B8.03.13 | 3rd Floor | B8 | Flat | 3 | 4 | 75.52 | 812.8973 | S/O | [7 empty] | 812.8973 | [24 empty] | 812.8973 | 0
| B8.03.14 | 3rd Floor | B8 | Flat | 1 | 2 | 50.76 | 546.3806 | S/O |  | 546.3806 | [30 empty] | 546.3806 | 0
| B8.03.15 | 3rd Floor | B8 | Flat | 2 | 3 | 75.81 | 816.0188 | S/O |  |  |  |  | 816.0188 | [27 empty] | 816.0188 | 0
| B8.03.16 | 4th Floor | B8 | Flat | 2 | 3 | 75.81 | 816.0188 | S/O |  |  |  |  | 816.0188 | [27 empty] | 816.0188 | 0
| B8.04.17 | 4th Floor | B8 | Flat | 3 | 4 | 75.52 | 812.8973 | S/O | [7 empty] | 812.8973 | [24 empty] | 812.8973 | 0
| B8.04.18 | 4th Floor | B8 | Flat | 1 | 2 | 50.76 | 546.3806 | S/O |  | 546.3806 | [30 empty] | 546.3806 | 0
| B8.04.19 | 4th Floor | B8 | Flat | 2 | 3 | 75.81 | 816.0188 | S/O |  |  |  |  | 816.0188 | [27 empty] | 816.0188 | 0
| B8.04.20 | 5th Floor | B8 | Flat | 2 | 3 | 75.81 | 816.0188 | S/O |  |  |  |  | 816.0188 | [27 empty] | 816.0188 | 0
| B8.04.21 | 5th Floor | B8 | Flat | 3 | 4 | 75.52 | 812.8973 | S/O | [7 empty] | 812.8973 | [24 empty] | 812.8973 | 0
| B8.05.22 | 5th Floor | B8 | Flat | 1 | 2 | 50.76 | 546.3806 | S/O |  | 546.3806 | [30 empty] | 546.3806 | 0
| B8.05.23 | 5th Floor | B8 | Flat | 2 | 3 | 75.81 | 816.0188 | S/O |  |  |  |  | 816.0188 | [27 empty] | 816.0188 | 0
| B8.06.24 | 6th Floor | B8 | Flat | 2 | 3 | 75.76 | 815.4806 | S/O |  |  |  |  | 815.4806 | [27 empty] | 815.4806 | 0
| B8.06.25 | 6th Floor | B8 | Flat | 3 | 4 | 75.52 | 812.8973 | S/O | [7 empty] | 812.8973 | [24 empty] | 812.8973 | 0
| B8.06.26 | 6th Floor | B8 | Flat | 1 | 2 | 50.71 | 545.8424 | S/O |  | 545.8424 | [30 empty] | 545.8424 | 0
| B8.06.27 | 6th Floor | B8 | Flat | 2 | 3 | 75.81 | 816.0188 | S/O |  |  |  |  | 816.0188 | [27 empty] | 816.0188 | 0
B9 | B9.00.01 | Ground Floor | B9 | Flat | 1 | 2 | 50.37 | 542.1827 | S/O |  | 542.1827 | [30 empty] | 542.1827 | 0
| B9.00.02 | Ground Floor | B9 | Flat | 2 | 3 | 68.31 | 735.2888 | S/O |  |  |  |  | 735.2888 | [27 empty] | 735.2888 | 0
| B9.00.03 | Ground Floor | B9 | Flat | 2 | 3 | 65.39 | 703.858 | S/O |  |  |  |  | 703.858 | [27 empty] | 703.858 | 0
| B9.01.04 | 1st Floor | B9 | Flat | 0 | 1 | 37.24 | 400.8514 | S/O | 400.8514 | [31 empty] | 400.8514 | 0
| B9.01.05 | 1st Floor | B9 | Flat | 2 | 3 | 76.01 | 818.1716 | S/O |  |  |  |  | 818.1716 | [27 empty] | 818.1716 | 0
| B9.01.06 | 1st Floor | B9 | Flat | 2 | 3 | 68.48 | 737.1187 | S/O |  |  |  |  | 737.1187 | [27 empty] | 737.1187 | 0
| B9.01.07 | 1st Floor | B9 | Flat | 1 | 2 | 50.84 | 547.2418 | S/O |  | 547.2418 | [30 empty] | 547.2418 | 0
| B9.01.08 | 1st Floor | B9 | Flat | 2 | 3 | 68.45 | 736.7958 | S/O |  |  |  |  | 736.7958 | [27 empty] | 736.7958 | 0
| B9.01.09 | 1st Floor | B9 | Flat | 2 | 3 | 65.73 | 707.5177 | S/O |  |  |  |  | 707.5177 | [27 empty] | 707.5177 | 0
| B9.02.10 | 2nd Floor | B9 | Flat | 3 | 4 | 75.16 | 809.0222 | S/O | [7 empty] | 809.0222 | [24 empty] | 809.0222 | 0
| B9.02.11 | 2nd Floor | B9 | Flat | 2 | 3 | 67.97 | 731.6291 | S/O |  |  |  |  | 731.6291 | [27 empty] | 731.6291 | 0
| B9.02.12 | 2nd Floor | B9 | Flat | 2 | 3 | 68.63 | 738.7333 | S/O |  |  |  |  | 738.7333 | [27 empty] | 738.7333 | 0
| B9.02.13 | 2nd Floor | B9 | Flat | 1 | 2 | 50.82 | 547.0265 | S/O |  | 547.0265 | [30 empty] | 547.0265 | 0
| B9.02.14 | 2nd Floor | B9 | Flat | 1 | 2 | 50.82 | 547.0265 | S/O |  | 547.0265 | [30 empty] | 547.0265 | 0
| B9.02.15 | 2nd Floor | B9 | Flat | 2 | 3 | 68.48 | 737.1187 | S/O |  |  |  |  | 737.1187 | [27 empty] | 737.1187 | 0
| B9.02.16 | 2nd Floor | B9 | Flat | 2 | 3 | 65.76 | 707.8406 | S/O |  |  |  |  | 707.8406 | [27 empty] | 707.8406 | 0
| B9.03.17 | 3rd Floor | B9 | Flat | 3 | 4 | 75.16 | 809.0222 | S/O | [7 empty] | 809.0222 | [24 empty] | 809.0222 | 0
| B9.03.18 | 3rd Floor | B9 | Flat | 2 | 3 | 67.97 | 731.6291 | S/O |  |  |  |  | 731.6291 | [27 empty] | 731.6291 | 0
| B9.03.19 | 3rd Floor | B9 | Flat | 2 | 3 | 68.63 | 738.7333 | S/O |  |  |  |  | 738.7333 | [27 empty] | 738.7333 | 0
| B9.03.20 | 3rd Floor | B9 | Flat | 1 | 2 | 50.82 | 547.0265 | S/O |  | 547.0265 | [30 empty] | 547.0265 | 0
| B9.03.21 | 3rd Floor | B9 | Flat | 1 | 2 | 50.82 | 547.0265 | S/O |  | 547.0265 | [30 empty] | 547.0265 | 0
| B9.03.22 | 3rd Floor | B9 | Flat | 2 | 3 | 68.59 | 738.3028 | S/O |  |  |  |  | 738.3028 | [27 empty] | 738.3028 | 0
| B9.03.23 | 3rd Floor | B9 | Flat | 2 | 3 | 65.76 | 707.8406 | S/O |  |  |  |  | 707.8406 | [27 empty] | 707.8406 | 0
C1 | C1.00.01 | Level 0-1 | C1 | Duplex | 2 | 3 | 86.4 | 930.0096 | S/O | [5 empty] | 930.0096 | [26 empty] | 930.0096 | 0
| C1.00.02 | Level 0-1 | C1 | Duplex | 2 | 3 | 86.4 | 930.0096 | S/O | [5 empty] | 930.0096 | [26 empty] | 930.0096 | 0
| C1.00.03 | Level 0-1 | C1 | Duplex | 2 | 3 | 86.4 | 930.0096 | S/O | [5 empty] | 930.0096 | [26 empty] | 930.0096 | 0
| C1.01.04 | Level 1 | C1 | Flat | 1 | 2 | 56.6 | 609.2424 | Rented | [17 empty] | 609.2424 | [14 empty] | 609.2424 | 0
| C1.01.05 | Level 1 | C1 | Flat | 1 | 2 | 63.6 | 684.5904 | Rented | [17 empty] | 684.5904 | [14 empty] | 684.5904 | 0
| C1.01.06 | Level 1 | C1 | Flat | 1 | 2 | 51.2 | 551.1168 | Rented | [17 empty] | 551.1168 | [14 empty] | 551.1168 | 0
| C1.01.07 | Level 1 | C1 | Flat | 1 | 2 | 51.2 | 551.1168 | Rented | [17 empty] | 551.1168 | [14 empty] | 551.1168 | 0
| C1.01.08 | Level 1 | C1 | Flat | 1 | 2 | 51.3 | 552.1932 | Rented | [17 empty] | 552.1932 | [14 empty] | 552.1932 | 0
| C1.02.09 | Level 2 | C1 | Flat | 2 | 3 | 68.9 | 741.6396 | Rented | [20 empty] | 741.6396 | [11 empty] | 741.6396 | 0
| C1.02.10 | Level 2 | C1 | Flat | 1 | 2 | 51.2 | 551.1168 | Rented | [17 empty] | 551.1168 | [14 empty] | 551.1168 | 0
| C1.02.11 | Level 2 | C1 | Flat | 1 | 2 | 51.2 | 551.1168 | Rented | [17 empty] | 551.1168 | [14 empty] | 551.1168 | 0
| C1.02.12 | Level 2 | C1 | Flat | 2 | 3 | 72.2 | 777.1608 | Rented | [20 empty] | 777.1608 | [11 empty] | 777.1608 | 0
| C1.02.13 | Level 2 | C1 | Flat | 1 | 2 | 50.2 | 540.3528 | Rented | [17 empty] | 540.3528 | [14 empty] | 540.3528 | 0
| C1.02.14 | Level 2 | C1 | Flat | 1 | 2 | 58.1 | 625.3884 | Rented | [17 empty] | 625.3884 | [14 empty] | 625.3884 | 0
| C1.02.15 | Level 2 | C1 | Flat | 1 | 2 | 63.6 | 684.5904 | Rented | [17 empty] | 684.5904 | [14 empty] | 684.5904 | 0
| C1.02.16 | Level 2 | C1 | Flat | 1 | 2 | 51.3 | 552.1932 | Rented | [17 empty] | 552.1932 | [14 empty] | 552.1932 | 0
| C1.03.17 | Level 3 | C1 | Flat | 2 | 3 | 68.9 | 741.6396 | Rented | [20 empty] | 741.6396 | [11 empty] | 741.6396 | 0
| C1.03.18 | Level 3 | C1 | Flat | 1 | 2 | 51.2 | 551.1168 | Rented | [17 empty] | 551.1168 | [14 empty] | 551.1168 | 0
| C1.03.19 | Level 3 | C1 | Flat | 1 | 2 | 51.2 | 551.1168 | Rented | [17 empty] | 551.1168 | [14 empty] | 551.1168 | 0
| C1.03.20 | Level 3 | C1 | Flat | 2 | 3 | 72.2 | 777.1608 | Rented | [20 empty] | 777.1608 | [11 empty] | 777.1608 | 0
| C1.03.21 | Level 3 | C1 | Flat | 1 | 2 | 50.2 | 540.3528 | Rented | [17 empty] | 540.3528 | [14 empty] | 540.3528 | 0
| C1.03.22 | Level 3 | C1 | Flat | 1 | 2 | 58.1 | 625.3884 | Rented | [17 empty] | 625.3884 | [14 empty] | 625.3884 | 0
| C1.03.23 | Level 3 | C1 | Flat | 1 | 2 | 63.6 | 684.5904 | Rented | [17 empty] | 684.5904 | [14 empty] | 684.5904 | 0
| C1.03.24 | Level 3 | C1 | Flat | 1 | 2 | 51.3 | 552.1932 | Rented | [17 empty] | 552.1932 | [14 empty] | 552.1932 | 0
| C1.04.25 | Level 4 | C1 | Flat | 1 | 2 | 51.3 | 552.1932 | Rented | [17 empty] | 552.1932 | [14 empty] | 552.1932 | 0
| C1.04.26 | Level 4 | C1 | Flat | 2 | 3 | 69.8 | 751.3272 | Rented | [20 empty] | 751.3272 | [11 empty] | 751.3272 | 0
| C1.04.27 | Level 4 | C1 | Flat | 1 | 2 | 63.6 | 684.5904 | Rented | [17 empty] | 684.5904 | [14 empty] | 684.5904 | 0
| C1.04.28 | Level 4 | C1 | Flat | 1 | 2 | 56.9 | 612.4716 | Rented | [17 empty] | 612.4716 | [14 empty] | 612.4716 | 0
| C1.05.29 | Level 5 | C1 | Flat | 1 | 2 | 51.3 | 552.1932 | Rented | [17 empty] | 552.1932 | [14 empty] | 552.1932 | 0
| C1.05.30 | Level 5 | C1 | Flat | 2 | 3 | 69.8 | 751.3272 | Rented | [20 empty] | 751.3272 | [11 empty] | 751.3272 | 0
| C1.05.31 | Level 5 | C1 | Flat | 1 | 2 | 63.6 | 684.5904 | Rented | [17 empty] | 684.5904 | [14 empty] | 684.5904 | 0
| C1.05.32 | Level 5 | C1 | Flat | 1 | 2 | 56.9 | 612.4716 | Rented | [17 empty] | 612.4716 | [14 empty] | 612.4716 | 0
C2 | C2.00.01 | Level 0-1 | C2 | Duplex | 3 | 4 | 95.4 | 1026.8856 | Rented | [24 empty] | 1026.8856 | [7 empty] | 1026.8856 | 0
| C2.00.02 | Level 0-1 | C2 | Duplex | 2 | 3 | 82.2 | 884.8008 | S/O | [5 empty] | 884.8008 | [26 empty] | 884.8008 | 0
| C2.00.04 | Level 0-1 | C2 | Duplex | 2 | 3 | 84.2 | 906.3288 | S/O | [5 empty] | 906.3288 | [26 empty] | 906.3288 | 0
| C2.00.05 | Level 0-1 | C2 | Duplex | 2 | 3 | 85.6 | 921.3984 | S/O | [5 empty] | 921.3984 | [26 empty] | 921.3984 | 0
C3 | C3.00.01 | Level 0-1 | C3 | Duplex | 3 | 4 | 99.2 | 1067.7888 | Rented | [24 empty] | 1067.7888 | [7 empty] | 1067.7888 | 0
| C3.00.02 | Level 0-1 | C3 | Duplex | 3 | 4 | 99.2 | 1067.7888 | Rented | [24 empty] | 1067.7888 | [7 empty] | 1067.7888 | 0
| C3.00.03 | Level 0-1 | C3 | Duplex | 3 | 4 | 99.2 | 1067.7888 | Rented | [24 empty] | 1067.7888 | [7 empty] | 1067.7888 | 0
C4 | C4.00.01 | Level 0-1 | C4 | Duplex | 2 | 3 | 82.2 | 884.8008 | S/O | [5 empty] | 884.8008 | [26 empty] | 884.8008 | 0
| C4.00.02 | Level 0-1 | C4 | Duplex | 2 | 3 | 84.2 | 906.3288 | S/O | [5 empty] | 906.3288 | [26 empty] | 906.3288 | 0
| C4.00.03 | Level 0-1 | C4 | Duplex | 3 | 4 | 95.4 | 1026.8856 | Rented | [24 empty] | 1026.8856 | [7 empty] | 1026.8856 | 0
| C4.00.05 | Level 0-1 | C4 | Duplex | 2 | 3 | 85.6 | 921.3984 | S/O | [5 empty] | 921.3984 | [26 empty] | 921.3984 | 0
C5 | C5.00.01 | Level 0-1 | C5 | Duplex | 2 | 3 | 87.2 | 938.6208 | S/O | [5 empty] | 938.6208 | [26 empty] | 938.6208 | 0
| C5.00.02 | Level 0-1 | C5 | Duplex | 2 | 3 | 86.4 | 930.0096 | S/O | [5 empty] | 930.0096 | [26 empty] | 930.0096 | 0
| C5.00.03 | Level 0-1 | C5 | Duplex | 2 | 3 | 86.4 | 930.0096 | S/O | [5 empty] | 930.0096 | [26 empty] | 930.0096 | 0
| C5.00.04 | Level 0-1 | C5 | Duplex | 2 | 3 | 85.9 | 924.6276 | S/O | [5 empty] | 924.6276 | [26 empty] | 924.6276 | 0
C6 | C6.00.01 | 0 | C6 | Duplex | 3 | 4 | 113.1 | 1217.4084 | Rented | [24 empty] | 1217.4084 | [7 empty] | 1217.4084 | 0
| C6.00.02 | 0 | C6 | Duplex | 3 | 4 | 113.1 | 1217.4084 | Rented | [24 empty] | 1217.4084 | [7 empty] | 1217.4084 | 0
| C6.00.03 | 0 | C6 | Duplex | 3 | 4 | 111.7 | 1202.3388 | Rented | [24 empty] | 1202.3388 | [7 empty] | 1202.3388 | 0
| C6.00.04 | 0 | C6 | Duplex | 3 | 4 | 111.7 | 1202.3388 | Rented | [24 empty] | 1202.3388 | [7 empty] | 1202.3388 | 0
| C6.00.05 | 0 | C6 | Duplex | 3 | 4 | 107.2 | 1153.9008 | Rented | [24 empty] | 1153.9008 | [7 empty] | 1153.9008 | 0
| C6.00.06 | 0 | C6 | Duplex | 3 | 4 | 107.2 | 1153.9008 | Rented | [24 empty] | 1153.9008 | [7 empty] | 1153.9008 | 0
D1 | D1.00.01 | Level 0-1 | D1 | Duplex | 2 | 3 | 84.2 | 906.3288 | S/O | [5 empty] | 906.3288 | [26 empty] | 906.3288 | 0
| D1.00.02 | Level 0-1 | D1 | Duplex | 2 | 3 | 85.6 | 921.3984 | S/O | [5 empty] | 921.3984 | [26 empty] | 921.3984 | 0
| D1.00.03 | Level 0-1 | D1 | Duplex | 2 | 3 | 84.2 | 906.3288 | S/O | [5 empty] | 906.3288 | [26 empty] | 906.3288 | 0
| D1.00.04 | Level 0 | D1 | Flat | 1 | 2 | 55.6 | 598.4784 | Rented | [17 empty] | 598.4784 | [14 empty] | 598.4784 | 0
| D1.00.05 | Level 0-1 | D1 | Duplex | 3 | 4 | 94 | 1011.816 | Rented | [24 empty] | 1011.816 | [7 empty] | 1011.816 | 0
| D1.01.06 | Level 1 | D1 | Flat | 1 | 2 | 51.2 | 551.1168 | Rented | [17 empty] | 551.1168 | [14 empty] | 551.1168 | 0
| D1.01.07 | Level 1 | D1 | Flat | 1 | 2 | 51.2 | 551.1168 | Rented | [17 empty] | 551.1168 | [14 empty] | 551.1168 | 0
| D1.01.08 | Level 1 | D1 | Flat | 1 | 2 | 65 | 699.66 | Rented | [17 empty] | 699.66 | [14 empty] | 699.66 | 0
| D1.01.09 | Level 1 | D1 | Flat | 2 | 3 | 78.1 | 840.6684 | Rented | [20 empty] | 840.6684 | [11 empty] | 840.6684 | 0
| D1.02.10 | Level 2 | D1 | Flat | 2 | 3 | 68.9 | 741.6396 | Rented | [20 empty] | 741.6396 | [11 empty] | 741.6396 | 0
| D1.02.11 | Level 2 | D1 | Flat | 1 | 2 | 51.2 | 551.1168 | Rented | [17 empty] | 551.1168 | [14 empty] | 551.1168 | 0
| D1.02.12 | Level 2 | D1 | Flat | 1 | 2 | 51.2 | 551.1168 | Rented | [17 empty] | 551.1168 | [14 empty] | 551.1168 | 0
| D1.02.13 | Level 2 | D1 | Flat | 1 | 2 | 55.1 | 593.0964 | Rented | [17 empty] | 593.0964 | [14 empty] | 593.0964 | 0
| D1.02.14 | Level 2 | D1 | Flat | 2 | 3 | 70.1 | 754.5564 | Rented | [20 empty] | 754.5564 | [11 empty] | 754.5564 | 0
| D1.02.15 | Level 2 | D1 | Flat | 2 | 3 | 66.5 | 715.806 | Rented | [20 empty] | 715.806 | [11 empty] | 715.806 | 0
| D1.02.16 | Level 2 | D1 | Flat | 1 | 2 | 50 | 538.2 | Rented | [17 empty] | 538.2 | [14 empty] | 538.2 | 0
| D1.02.17 | Level 2 | D1 | Flat | 1 | 2 | 52.4 | 564.0336 | Rented | [17 empty] | 564.0336 | [14 empty] | 564.0336 | 0
| D1.03.18 | Level 3 | D1 | Flat | 2 | 3 | 68.9 | 741.6396 | Rented | [20 empty] | 741.6396 | [11 empty] | 741.6396 | 0
| D1.03.19 | Level 3 | D1 | Flat | 1 | 2 | 51.2 | 551.1168 | Rented | [17 empty] | 551.1168 | [14 empty] | 551.1168 | 0
| D1.03.20 | Level 3 | D1 | Flat | 1 | 2 | 51.2 | 551.1168 | Rented | [17 empty] | 551.1168 | [14 empty] | 551.1168 | 0
| D1.03.21 | Level 3 | D1 | Flat | 1 | 2 | 55.1 | 593.0964 | Rented | [17 empty] | 593.0964 | [14 empty] | 593.0964 | 0
| D1.03.22 | Level 3 | D1 | Flat | 2 | 3 | 70.1 | 754.5564 | Rented | [20 empty] | 754.5564 | [11 empty] | 754.5564 | 0
| D1.03.23 | Level 3 | D1 | Flat | 2 | 3 | 66.5 | 715.806 | Rented | [20 empty] | 715.806 | [11 empty] | 715.806 | 0
| D1.03.24 | Level 3 | D1 | Flat | 1 | 2 | 50 | 538.2 | Rented | [17 empty] | 538.2 | [14 empty] | 538.2 | 0
| D1.03.25 | Level 3 | D1 | Flat | 1 | 2 | 52.4 | 564.0336 | Rented | [17 empty] | 564.0336 | [14 empty] | 564.0336 | 0
| D1.04.26 | Level 4 | D1 | Flat | 2 | 3 | 68.9 | 741.6396 | Rented | [20 empty] | 741.6396 | [11 empty] | 741.6396 | 0
| D1.04.27 | Level 4 | D1 | Flat | 1 | 2 | 51.2 | 551.1168 | Rented | [17 empty] | 551.1168 | [14 empty] | 551.1168 | 0
| D1.04.28 | Level 4 | D1 | Flat | 1 | 2 | 51.2 | 551.1168 | Rented | [17 empty] | 551.1168 | [14 empty] | 551.1168 | 0
| D1.04.29 | Level 4 | D1 | Flat | 1 | 2 | 55.1 | 593.0964 | Rented | [17 empty] | 593.0964 | [14 empty] | 593.0964 | 0
| D1.04.30 | Level 4 | D1 | Flat | 2 | 3 | 70.1 | 754.5564 | Rented | [20 empty] | 754.5564 | [11 empty] | 754.5564 | 0
| D1.04.31 | Level 4 | D1 | Flat | 2 | 3 | 66.5 | 715.806 | Rented | [20 empty] | 715.806 | [11 empty] | 715.806 | 0
| D1.04.32 | Level 4 | D1 | Flat | 1 | 2 | 50 | 538.2 | Rented | [17 empty] | 538.2 | [14 empty] | 538.2 | 0
| D1.04.33 | Level 4 | D1 | Flat | 1 | 2 | 52.4 | 564.0336 | Rented | [17 empty] | 564.0336 | [14 empty] | 564.0336 | 0
| D1.05.34 | Level 5 | D1 | Flat | 2 | 3 | 68.9 | 741.6396 | Rented | [20 empty] | 741.6396 | [11 empty] | 741.6396 | 0
| D1.05.35 | Level 5 | D1 | Flat | 1 | 2 | 51.2 | 551.1168 | Rented | [17 empty] | 551.1168 | [14 empty] | 551.1168 | 0
| D1.05.36 | Level 5 | D1 | Flat | 1 | 2 | 51.2 | 551.1168 | Rented | [17 empty] | 551.1168 | [14 empty] | 551.1168 | 0
| D1.05.37 | Level 5 | D1 | Flat | 2 | 3 | 68.9 | 741.6396 | Rented | [20 empty] | 741.6396 | [11 empty] | 741.6396 | 0
| D1.05.38 | Level 5 | D1 | Flat | 2 | 3 | 70.1 | 754.5564 | Rented | [20 empty] | 754.5564 | [11 empty] | 754.5564 | 0
| D1.05.39 | Level 5 | D1 | Flat | 2 | 3 | 66.5 | 715.806 | Rented | [20 empty] | 715.806 | [11 empty] | 715.806 | 0
| D1.05.40 | Level 5 | D1 | Flat | 1 | 2 | 50 | 538.2 | Rented | [17 empty] | 538.2 | [14 empty] | 538.2 | 0
| D1.05.41 | Level 5 | D1 | Flat | 1 | 2 | 52.4 | 564.0336 | Rented | [17 empty] | 564.0336 | [14 empty] | 564.0336 | 0
| D1.06.42 | Level 6 | D1 | Flat | 2 | 3 | 68.9 | 741.6396 | Rented | [20 empty] | 741.6396 | [11 empty] | 741.6396 | 0
| D1.06.43 | Level 6 | D1 | Flat | 1 | 2 | 51.2 | 551.1168 | Rented | [17 empty] | 551.1168 | [14 empty] | 551.1168 | 0
| D1.06.44 | Level 6 | D1 | Flat | 1 | 2 | 51.2 | 551.1168 | Rented | [17 empty] | 551.1168 | [14 empty] | 551.1168 | 0
| D1.06.45 | Level 6 | D1 | Flat | 2 | 3 | 68.9 | 741.6396 | Rented | [20 empty] | 741.6396 | [11 empty] | 741.6396 | 0
| D1.06.46 | Level 6 | D1 | Flat | 2 | 3 | 70.1 | 754.5564 | Rented | [20 empty] | 754.5564 | [11 empty] | 754.5564 | 0
| D1.06.47 | Level 6 | D1 | Flat | 2 | 3 | 66.5 | 715.806 | Rented | [20 empty] | 715.806 | [11 empty] | 715.806 | 0
| D1.06.48 | Level 6 | D1 | Flat | 1 | 2 | 50 | 538.2 | Rented | [17 empty] | 538.2 | [14 empty] | 538.2 | 0
| D1.06.49 | Level 6 | D1 | Flat | 1 | 2 | 52.4 | 564.0336 | Rented | [17 empty] | 564.0336 | [14 empty] | 564.0336 | 0
| D1.07.50 | Level 7 | D1 | Flat | 2 | 3 | 68.9 | 741.6396 | Rented | [20 empty] | 741.6396 | [11 empty] | 741.6396 | 0
| D1.07.51 | Level 7 | D1 | Flat | 1 | 2 | 51.2 | 551.1168 | Rented | [17 empty] | 551.1168 | [14 empty] | 551.1168 | 0
| D1.07.52 | Level 7 | D1 | Flat | 1 | 2 | 51.2 | 551.1168 | Rented | [17 empty] | 551.1168 | [14 empty] | 551.1168 | 0
| D1.07.53 | Level 7 | D1 | Flat | 2 | 3 | 68.9 | 741.6396 | Rented | [20 empty] | 741.6396 | [11 empty] | 741.6396 | 0
| D1.07.54 | Level 7 | D1 | Flat | 2 | 3 | 70.1 | 754.5564 | Rented | [20 empty] | 754.5564 | [11 empty] | 754.5564 | 0
| D1.07.55 | Level 7 | D1 | Flat | 2 | 3 | 66.5 | 715.806 | Rented | [20 empty] | 715.806 | [11 empty] | 715.806 | 0
| D1.07.56 | Level 7 | D1 | Flat | 1 | 2 | 50 | 538.2 | Rented | [17 empty] | 538.2 | [14 empty] | 538.2 | 0
| D1.07.57 | Level 7 | D1 | Flat | 1 | 2 | 52.4 | 564.0336 | Rented | [17 empty] | 564.0336 | [14 empty] | 564.0336 | 0
| D1.08.58 | Level 8 | D1 | Flat | 2 | 3 | 68.9 | 741.6396 | Rented | [20 empty] | 741.6396 | [11 empty] | 741.6396 | 0
| D1.08.59 | Level 8 | D1 | Flat | 1 | 2 | 51.2 | 551.1168 | Rented | [17 empty] | 551.1168 | [14 empty] | 551.1168 | 0
| D1.08.60 | Level 8 | D1 | Flat | 1 | 2 | 51.2 | 551.1168 | Rented | [17 empty] | 551.1168 | [14 empty] | 551.1168 | 0
| D1.08.61 | Level 8 | D1 | Flat | 2 | 3 | 68.9 | 741.6396 | Rented | [20 empty] | 741.6396 | [11 empty] | 741.6396 | 0
| D1.08.62 | Level 8 | D1 | Flat | 2 | 3 | 70.1 | 754.5564 | Rented | [20 empty] | 754.5564 | [11 empty] | 754.5564 | 0
| D1.08.63 | Level 8 | D1 | Flat | 2 | 3 | 66.5 | 715.806 | Rented | [20 empty] | 715.806 | [11 empty] | 715.806 | 0
| D1.08.64 | Level 8 | D1 | Flat | 1 | 2 | 50 | 538.2 | Rented | [17 empty] | 538.2 | [14 empty] | 538.2 | 0
| D1.08.65 | Level 8 | D1 | Flat | 1 | 2 | 52.4 | 564.0336 | Rented | [17 empty] | 564.0336 | [14 empty] | 564.0336 | 0
| D1.09.66 | Level 9 | D1 | Flat | 2 | 3 | 68.9 | 741.6396 | Rented | [20 empty] | 741.6396 | [11 empty] | 741.6396 | 0
| D1.09.67 | Level 9 | D1 | Flat | 1 | 2 | 51.2 | 551.1168 | Rented | [17 empty] | 551.1168 | [14 empty] | 551.1168 | 0
| D1.09.68 | Level 9 | D1 | Flat | 1 | 2 | 51.2 | 551.1168 | Rented | [17 empty] | 551.1168 | [14 empty] | 551.1168 | 0
| D1.09.69 | Level 9 | D1 | Flat | 2 | 3 | 68.9 | 741.6396 | Rented | [20 empty] | 741.6396 | [11 empty] | 741.6396 | 0
| D1.09.70 | Level 9 | D1 | Flat | 2 | 3 | 70.1 | 754.5564 | Rented | [20 empty] | 754.5564 | [11 empty] | 754.5564 | 0
| D1.09.71 | Level 9 | D1 | Flat | 2 | 3 | 66.5 | 715.806 | Rented | [20 empty] | 715.806 | [11 empty] | 715.806 | 0
| D1.09.72 | Level 9 | D1 | Flat | 1 | 2 | 50 | 538.2 | Rented | [17 empty] | 538.2 | [14 empty] | 538.2 | 0
| D1.09.73 | Level 9 | D1 | Flat | 1 | 2 | 52.4 | 564.0336 | Rented | [17 empty] | 564.0336 | [14 empty] | 564.0336 | 0
D2 | D2.00.01 | Level 0-1 | D2 | Duplex | 2 | 3 | 86.4 | 930.0096 | S/O | [5 empty] | 930.0096 | [26 empty] | 930.0096 | 0
| D2.00.02 | Level 0-1 | D2 | Duplex | 2 | 3 | 84.2 | 906.3288 | S/O | [5 empty] | 906.3288 | [26 empty] | 906.3288 | 0
| D2.00.03 | Level 0-1 | D2 | Duplex | 2 | 3 | 86.5 | 931.086 | S/O | [5 empty] | 931.086 | [26 empty] | 931.086 | 0
| D2.01.04 | Level 1 | D2 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| D2.01.05 | Level 1 | D2 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| D2.01.06 | Level 1 | D2 | Flat | 0 | 1 | 38.5 | 414.414 | S/O | 414.414 | [31 empty] | 414.414 | 0
| D2.01.07 | Level 1 | D2 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| D2.01.08 | Level 1 | D2 | Flat | 2 | 3 | 78.1 | 840.6684 | S/O |  |  |  |  | 840.6684 | [27 empty] | 840.6684 | 0
| D2.02.09 | Level 2 | D2 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| D2.02.10 | Level 2 | D2 | Flat | 1 | 2 | 55.4 | 596.3256 | S/O |  | 596.3256 | [30 empty] | 596.3256 | 0
| D2.02.11 | Level 2 | D2 | Flat | 2 | 3 | 68.9 | 741.6396 | S/O |  |  |  |  | 741.6396 | [27 empty] | 741.6396 | 0
| D2.02.12 | Level 2 | D2 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| D2.02.13 | Level 2 | D2 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| D2.02.14 | Level 2 | D2 | Flat | 1 | 2 | 61.7 | 664.1388 | S/O |  | 664.1388 | [30 empty] | 664.1388 | 0
| D2.02.15 | Level 2 | D2 | Flat | 0 | 1 | 38.5 | 414.414 | S/O | 414.414 | [31 empty] | 414.414 | 0
| D2.02.16 | Level 2 | D2 | Flat | 1 | 2 | 50.2 | 540.3528 | S/O |  | 540.3528 | [30 empty] | 540.3528 | 0
| D2.03.17 | Level 3 | D2 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| D2.03.18 | Level 3 | D2 | Flat | 1 | 2 | 55.4 | 596.3256 | S/O |  | 596.3256 | [30 empty] | 596.3256 | 0
| D2.03.19 | Level 3 | D2 | Flat | 2 | 3 | 68.9 | 741.6396 | S/O |  |  |  |  | 741.6396 | [27 empty] | 741.6396 | 0
| D2.03.20 | Level 3 | D2 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| D2.03.21 | Level 3 | D2 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| D2.03.22 | Level 3 | D2 | Flat | 1 | 2 | 61.7 | 664.1388 | S/O |  | 664.1388 | [30 empty] | 664.1388 | 0
| D2.03.23 | Level 3 | D2 | Flat | 0 | 1 | 38.5 | 414.414 | S/O | 414.414 | [31 empty] | 414.414 | 0
| D2.03.24 | Level 3 | D2 | Flat | 1 | 2 | 50.2 | 540.3528 | S/O |  | 540.3528 | [30 empty] | 540.3528 | 0
| D2.04.25 | Level 4 | D2 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| D2.04.26 | Level 4 | D2 | Flat | 1 | 2 | 55.4 | 596.3256 | S/O |  | 596.3256 | [30 empty] | 596.3256 | 0
| D2.04.27 | Level 4 | D2 | Flat | 2 | 3 | 68.9 | 741.6396 | S/O |  |  |  |  | 741.6396 | [27 empty] | 741.6396 | 0
| D2.04.28 | Level 4 | D2 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| D2.04.29 | Level 4 | D2 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| D2.04.30 | Level 4 | D2 | Flat | 1 | 2 | 61.7 | 664.1388 | S/O |  | 664.1388 | [30 empty] | 664.1388 | 0
| D2.04.31 | Level 4 | D2 | Flat | 0 | 1 | 38.5 | 414.414 | S/O | 414.414 | [31 empty] | 414.414 | 0
| D2.04.32 | Level 4 | D2 | Flat | 1 | 2 | 50.2 | 540.3528 | S/O |  | 540.3528 | [30 empty] | 540.3528 | 0
| D2.05.33 | Level 5 | D2 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| D2.05.34 | Level 5 | D2 | Flat | 0 | 1 | 38.5 | 414.414 | S/O | 414.414 | [31 empty] | 414.414 | 0
| D2.05.35 | Level 5 | D2 | Flat | 1 | 2 | 53.9 | 580.1796 | S/O |  | 580.1796 | [30 empty] | 580.1796 | 0
| D2.05.36 | Level 5 | D2 | Flat | 2 | 3 | 69.8 | 751.3272 | S/O |  |  |  |  | 751.3272 | [27 empty] | 751.3272 | 0
D3 | D3.00.01 | Level 0 | D3 | Duplex | 2 | 3 | 85.4 | 919.2456 | S/O | [5 empty] | 919.2456 | [26 empty] | 919.2456 | 0
| D3.00.02 | Level 0 | D3 | Duplex | 3 | 4 | 111.7 | 1202.3388 | Rented | [24 empty] | 1202.3388 | [7 empty] | 1202.3388 | 0
| D3.00.03 | Level 0 | D3 | Duplex | 3 | 4 | 113.1 | 1217.4084 | Rented | [24 empty] | 1217.4084 | [7 empty] | 1217.4084 | 0
| D3.00.04 | Level 2 | D3 | Flat | 0 | 1 | 38.6 | 415.4904 | S/O | 415.4904 | [31 empty] | 415.4904 | 0
| D3.00.05 | Level 2 | D3 | Flat | 2 | 3 | 74.8 | 805.1472 | S/O |  |  |  |  | 805.1472 | [27 empty] | 805.1472 | 0
| D3.00.06 | Level 2 | D3 | Flat | 2 | 3 | 65.8 | 708.2712 | S/O |  |  |  |  | 708.2712 | [27 empty] | 708.2712 | 0
| D3.00.07 | Level 3 | D3 | Flat | 0 | 1 | 38.6 | 415.4904 | S/O | 415.4904 | [31 empty] | 415.4904 | 0
| D3.00.08 | Level 3 | D3 | Flat | 2 | 3 | 74.8 | 805.1472 | S/O |  |  |  |  | 805.1472 | [27 empty] | 805.1472 | 0
| D3.00.08 | Level 3 | D3 | Flat | 2 | 3 | 65.8 | 708.2712 | S/O |  |  |  |  | 708.2712 | [27 empty] | 708.2712 | 0
D4 | D4.00.01 | Level 2 | D4 | Flat | 1 | 2 | 51.4 | 553.2696 | S/O |  | 553.2696 | [30 empty] | 553.2696 | 0
| D4.00.02 | Level 2 | D4 | Flat | 3 | 4 | 91.1 | 980.6004 | S/O | [7 empty] | 980.6004 | [24 empty] | 980.6004 | 0
| D4.00.03 | Level 3 | D4 | Flat | 1 | 2 | 51.4 | 553.2696 | S/O |  | 553.2696 | [30 empty] | 553.2696 | 0
| D4.00.04 | Level 3 | D4 | Flat | 3 | 4 | 91.1 | 980.6004 | S/O | [7 empty] | 980.6004 | [24 empty] | 980.6004 | 0
| D4.00.05 | Level 4 | D4 | Flat | 1 | 2 | 51.4 | 553.2696 | S/O |  | 553.2696 | [30 empty] | 553.2696 | 0
| D4.00.06 | Level 4 | D4 | Flat | 3 | 4 | 91.1 | 980.6004 | S/O | [7 empty] | 980.6004 | [24 empty] | 980.6004 | 0
E1 | E1.00.01 | Level 0-1 | E1 | Duplex | 2 | 3 | 83 | 893.412 | S/O | [5 empty] | 893.412 | [26 empty] | 893.412 | 0
| E1.00.02 | Level 0-1 | E1 | Duplex | 2 | 3 | 74.4 | 800.8416 | S/O | [5 empty] | 800.8416 | [26 empty] | 800.8416 | 0
| E1.00.03 | Level 0-1 | E1 | Duplex | 2 | 3 | 74.4 | 800.8416 | S/O | [5 empty] | 800.8416 | [26 empty] | 800.8416 | 0
| E1.00.04 | Level 0-1 | E1 | Duplex | 2 | 3 | 86.6 | 932.1624 | S/O | [5 empty] | 932.1624 | [26 empty] | 932.1624 | 0
| E1.00.05 | Level 0-1 | E1 | Duplex | 2 | 3 | 86.6 | 932.1624 | S/O | [5 empty] | 932.1624 | [26 empty] | 932.1624 | 0
| E1.00.06 | Level 0-1 | E1 | Duplex | 2 | 3 | 83 | 893.412 | S/O | [5 empty] | 893.412 | [26 empty] | 893.412 | 0
| E1.00.07 | Level 0-1 | E1 | Duplex | 3 | 4 | 105.8 | 1138.8312 | Rented | [24 empty] | 1138.8312 | [7 empty] | 1138.8312 | 0
| E1.00.08 | Level 0-1 | E1 | Duplex | 3 | 4 | 128.8 | 1386.4032 | Rented | [24 empty] | 1386.4032 | [7 empty] | 1386.4032 | 0
| E1.02.09 | Level 2 | E1 | Flat | 1 | 2 | 50 | 538.2 | S/O |  | 538.2 | [30 empty] | 538.2 | 0
| E1.02.10 | Level 2 | E1 | Flat | 1 | 2 | 50 | 538.2 | S/O |  | 538.2 | [30 empty] | 538.2 | 0
| E1.02.11 | Level 2 | E1 | Flat | 2 | 3 | 72.2 | 777.1608 | S/O |  |  |  |  | 777.1608 | [27 empty] | 777.1608 | 0
| E1.02.12 | Level 2 | E1 | Flat | 2 | 3 | 68.9 | 741.6396 | S/O |  |  |  |  | 741.6396 | [27 empty] | 741.6396 | 0
| E1.02.13 | Level 2 | E1 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| E1.02.14 | Level 2 | E1 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| E1.02.15 | Level 2 | E1 | Flat | 0 | 1 | 37.7 | 405.8028 | S/O | 405.8028 | [31 empty] | 405.8028 | 0
| E1.02.16 | Level 2 | E1 | Flat | 2 | 3 | 64 | 688.896 | S/O |  |  |  |  | 688.896 | [27 empty] | 688.896 | 0
| E1.02.17 | Level 2 | E1 | Flat | 0 | 1 | 38.8 | 417.6432 | S/O | 417.6432 | [31 empty] | 417.6432 | 0
| E1.02.18 | Level 2 | E1 | Flat | 1 | 2 | 53.4 | 574.7976 | S/O |  | 574.7976 | [30 empty] | 574.7976 | 0
| E1.02.19 | Level 2 | E1 | Flat | 2 | 3 | 70.8 | 762.0912 | S/O |  |  |  |  | 762.0912 | [27 empty] | 762.0912 | 0
| E1.02.20 | Level 2 | E1 | Flat | 3 | 4 | 86.8 | 934.3152 | S/O | [7 empty] | 934.3152 | [24 empty] | 934.3152 | 0
| E1.03.21 | Level 3 | E1 | Flat | 1 | 2 | 50 | 538.2 | S/O |  | 538.2 | [30 empty] | 538.2 | 0
| E1.03.22 | Level 3 | E1 | Flat | 1 | 2 | 50 | 538.2 | S/O |  | 538.2 | [30 empty] | 538.2 | 0
| E1.03.23 | Level 3 | E1 | Flat | 2 | 3 | 72.2 | 777.1608 | S/O |  |  |  |  | 777.1608 | [27 empty] | 777.1608 | 0
| E1.03.24 | Level 3 | E1 | Flat | 2 | 3 | 68.9 | 741.6396 | S/O |  |  |  |  | 741.6396 | [27 empty] | 741.6396 | 0
| E1.03.25 | Level 3 | E1 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| E1.03.26 | Level 3 | E1 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| E1.03.27 | Level 3 | E1 | Flat | 0 | 1 | 37.7 | 405.8028 | S/O | 405.8028 | [31 empty] | 405.8028 | 0
| E1.03.28 | Level 3 | E1 | Flat | 2 | 3 | 64 | 688.896 | S/O |  |  |  |  | 688.896 | [27 empty] | 688.896 | 0
| E1.03.29 | Level 3 | E1 | Flat | 0 | 1 | 38.8 | 417.6432 | S/O | 417.6432 | [31 empty] | 417.6432 | 0
| E1.03.30 | Level 3 | E1 | Flat | 1 | 2 | 53.4 | 574.7976 | S/O |  | 574.7976 | [30 empty] | 574.7976 | 0
| E1.03.31 | Level 3 | E1 | Flat | 2 | 3 | 70.8 | 762.0912 | S/O |  |  |  |  | 762.0912 | [27 empty] | 762.0912 | 0
| E1.03.32 | Level 3 | E1 | Flat | 3 | 4 | 86.8 | 934.3152 | S/O | [7 empty] | 934.3152 | [24 empty] | 934.3152 | 0
| E1.04.33 | Level 4 | E1 | Flat | 1 | 2 | 50 | 538.2 | S/O |  | 538.2 | [30 empty] | 538.2 | 0
| E1.04.34 | Level 4 | E1 | Flat | 1 | 2 | 50 | 538.2 | S/O |  | 538.2 | [30 empty] | 538.2 | 0
| E1.04.35 | Level 4 | E1 | Flat | 2 | 3 | 72.2 | 777.1608 | S/O |  |  |  |  | 777.1608 | [27 empty] | 777.1608 | 0
| E1.04.36 | Level 4 | E1 | Flat | 2 | 3 | 68.9 | 741.6396 | S/O |  |  |  |  | 741.6396 | [27 empty] | 741.6396 | 0
| E1.04.37 | Level 4 | E1 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| E1.04.38 | Level 4 | E1 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| E1.04.39 | Level 4 | E1 | Flat | 0 | 1 | 37.7 | 405.8028 | S/O | 405.8028 | [31 empty] | 405.8028 | 0
| E1.04.40 | Level 4 | E1 | Flat | 2 | 3 | 64 | 688.896 | S/O |  |  |  |  | 688.896 | [27 empty] | 688.896 | 0
| E1.04.41 | Level 4 | E1 | Flat | 0 | 1 | 38.8 | 417.6432 | S/O | 417.6432 | [31 empty] | 417.6432 | 0
| E1.04.42 | Level 4 | E1 | Flat | 1 | 2 | 53.4 | 574.7976 | S/O |  | 574.7976 | [30 empty] | 574.7976 | 0
| E1.04.43 | Level 4 | E1 | Flat | 2 | 3 | 70.8 | 762.0912 | S/O |  |  |  |  | 762.0912 | [27 empty] | 762.0912 | 0
| E1.04.44 | Level 4 | E1 | Flat | 3 | 4 | 86.8 | 934.3152 | S/O | [7 empty] | 934.3152 | [24 empty] | 934.3152 | 0
| E1.05.45 | Level 5 | E1 | Flat | 1 | 2 | 50 | 538.2 | S/O |  | 538.2 | [30 empty] | 538.2 | 0
| E1.05.46 | Level 5 | E1 | Flat | 1 | 2 | 50 | 538.2 | S/O |  | 538.2 | [30 empty] | 538.2 | 0
| E1.05.47 | Level 5 | E1 | Flat | 2 | 3 | 72.2 | 777.1608 | S/O |  |  |  |  | 777.1608 | [27 empty] | 777.1608 | 0
| E1.05.48 | Level 5 | E1 | Flat | 2 | 3 | 68.9 | 741.6396 | S/O |  |  |  |  | 741.6396 | [27 empty] | 741.6396 | 0
| E1.05.49 | Level 5 | E1 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| E1.05.50 | Level 5 | E1 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| E1.05.51 | Level 5 | E1 | Flat | 0 | 1 | 37.7 | 405.8028 | S/O | 405.8028 | [31 empty] | 405.8028 | 0
| E1.05.52 | Level 5 | E1 | Flat | 2 | 3 | 64 | 688.896 | S/O |  |  |  |  | 688.896 | [27 empty] | 688.896 | 0
| E1.05.53 | Level 5 | E1 | Flat | 0 | 1 | 38.8 | 417.6432 | S/O | 417.6432 | [31 empty] | 417.6432 | 0
| E1.05.54 | Level 5 | E1 | Flat | 1 | 2 | 53.4 | 574.7976 | S/O |  | 574.7976 | [30 empty] | 574.7976 | 0
| E1.05.55 | Level 5 | E1 | Flat | 2 | 3 | 70.8 | 762.0912 | S/O |  |  |  |  | 762.0912 | [27 empty] | 762.0912 | 0
| E1.05.56 | Level 5 | E1 | Flat | 3 | 4 | 86.8 | 934.3152 | S/O | [7 empty] | 934.3152 | [24 empty] | 934.3152 | 0
E2 | E2.00.01 | Level 0 | E2 | Duplex | 2 | 3 | 84.2 | 906.3288 | S/O | [5 empty] | 906.3288 | [26 empty] | 906.3288 | 0
| E2.00.02 | Level 0-1 | E2 | Duplex | 2 | 3 | 87.2 | 938.6208 | S/O | [5 empty] | 938.6208 | [26 empty] | 938.6208 | 0
| E2.00.03 | Level 0-1 | E2 | Duplex | 2 | 3 | 92.2 | 992.4408 | S/O | [5 empty] | 992.4408 | [26 empty] | 992.4408 | 0
| E2.00.04 | Level 0-1 | E2 | Duplex | 2 | 3 | 84.2 | 906.3288 | S/O | [5 empty] | 906.3288 | [26 empty] | 906.3288 | 0
| E2.00.05 | Level 0-1 | E2 | Duplex | 3 | 4 | 94 | 1011.816 | Rented | [24 empty] | 1011.816 | [7 empty] | 1011.816 | 0
| E2.00.06 | Level 0 | E2 | Flat | 1 | 2 | 55.6 | 598.4784 | S/O |  | 598.4784 | [30 empty] | 598.4784 | 0
| E2.01.07 | Level 1 | E2 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| E2.01.08 | Level 1 | E2 | Flat | 2 | 3 | 68.9 | 741.6396 | S/O |  |  |  |  | 741.6396 | [27 empty] | 741.6396 | 0
| E2.01.09 | Level 1 | E2 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| E2.01.10 | Level 1 | E2 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| E2.01.11 | Level 1 | E2 | Flat | 1 | 2 | 65 | 699.66 | S/O |  | 699.66 | [30 empty] | 699.66 | 0
| E2.02.12 | Level 2 | E2 | Flat | 1 | 2 | 55.1 | 593.0964 | S/O |  | 593.0964 | [30 empty] | 593.0964 | 0
| E2.02.13 | Level 2 | E2 | Flat | 2 | 3 | 66.5 | 715.806 | S/O |  |  |  |  | 715.806 | [27 empty] | 715.806 | 0
| E2.02.14 | Level 2 | E2 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| E2.02.15 | Level 2 | E2 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| E2.02.16 | Level 2 | E2 | Flat | 1 | 2 | 50 | 538.2 | S/O |  | 538.2 | [30 empty] | 538.2 | 0
| E2.02.17 | Level 2 | E2 | Flat | 1 | 2 | 52.4 | 564.0336 | S/O |  | 564.0336 | [30 empty] | 564.0336 | 0
| E2.02.18 | Level 2 | E2 | Flat | 2 | 3 | 68.9 | 741.6396 | S/O |  |  |  |  | 741.6396 | [27 empty] | 741.6396 | 0
| E2.02.19 | Level 2 | E2 | Flat | 2 | 3 | 70.1 | 754.5564 | S/O |  |  |  |  | 754.5564 | [27 empty] | 754.5564 | 0
| E2.03.20 | Level 3 | E2 | Flat | 1 | 2 | 55.1 | 593.0964 | S/O |  | 593.0964 | [30 empty] | 593.0964 | 0
| E2.03.21 | Level 3 | E2 | Flat | 2 | 3 | 66.5 | 715.806 | S/O |  |  |  |  | 715.806 | [27 empty] | 715.806 | 0
| E2.03.22 | Level 3 | E2 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| E2.03.23 | Level 3 | E2 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| E2.03.24 | Level 3 | E2 | Flat | 1 | 2 | 50 | 538.2 | S/O |  | 538.2 | [30 empty] | 538.2 | 0
| E2.03.25 | Level 3 | E2 | Flat | 1 | 2 | 52.4 | 564.0336 | S/O |  | 564.0336 | [30 empty] | 564.0336 | 0
| E2.03.26 | Level 3 | E2 | Flat | 2 | 3 | 68.9 | 741.6396 | S/O |  |  |  |  | 741.6396 | [27 empty] | 741.6396 | 0
| E2.03.27 | Level 3 | E2 | Flat | 2 | 3 | 70.1 | 754.5564 | S/O |  |  |  |  | 754.5564 | [27 empty] | 754.5564 | 0
| E2.04.28 | Level 4 | E2 | Flat | 1 | 2 | 55.1 | 593.0964 | S/O |  | 593.0964 | [30 empty] | 593.0964 | 0
| E2.04.29 | Level 4 | E2 | Flat | 2 | 3 | 66.5 | 715.806 | S/O |  |  |  |  | 715.806 | [27 empty] | 715.806 | 0
| E2.04.30 | Level 4 | E2 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| E2.04.31 | Level 4 | E2 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| E2.04.32 | Level 4 | E2 | Flat | 1 | 2 | 50 | 538.2 | S/O |  | 538.2 | [30 empty] | 538.2 | 0
| E2.04.33 | Level 4 | E2 | Flat | 1 | 2 | 52.4 | 564.0336 | S/O |  | 564.0336 | [30 empty] | 564.0336 | 0
| E2.04.34 | Level 4 | E2 | Flat | 2 | 3 | 68.9 | 741.6396 | S/O |  |  |  |  | 741.6396 | [27 empty] | 741.6396 | 0
| E2.04.35 | Level 4 | E2 | Flat | 2 | 3 | 70.1 | 754.5564 | S/O |  |  |  |  | 754.5564 | [27 empty] | 754.5564 | 0
| E2.05.36 | Level 5 | E2 | Flat | 2 | 3 | 68.9 | 741.6396 | S/O |  |  |  |  | 741.6396 | [27 empty] | 741.6396 | 0
| E2.05.37 | Level 5 | E2 | Flat | 2 | 3 | 68.9 | 741.6396 | S/O |  |  |  |  | 741.6396 | [27 empty] | 741.6396 | 0
| E2.05.38 | Level 5 | E2 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| E2.05.39 | Level 5 | E2 | Flat | 1 | 2 | 51.2 | 551.1168 | S/O |  | 551.1168 | [30 empty] | 551.1168 | 0
| E2.05.40 | Level 5 | E2 | Flat | 1 | 2 | 50 | 538.2 | S/O |  | 538.2 | [30 empty] | 538.2 | 0
| E2.05.41 | Level 5 | E2 | Flat | 1 | 2 | 52.4 | 564.0336 | S/O |  | 564.0336 | [30 empty] | 564.0336 | 0
| E2.05.42 | Level 5 | E2 | Flat | 2 | 3 | 66.5 | 715.806 | S/O |  |  |  |  | 715.806 | [27 empty] | 715.806 | 0
| E2.05.43 | Level 5 | E2 | Flat | 2 | 3 | 70.1 | 754.5564 | S/O |  |  |  |  | 754.5564 | [27 empty] | 754.5564 | 0
E3 | E3.00.01 | Level 1 | E3 | Flat | 1 | 2 | 59 | 635.076 | S/O |  | 635.076 | [30 empty] | 635.076 | 0
| E3.00.02 | Level 1 | E3 | Flat | 3 | 4 | 91.1 | 980.6004 | S/O | [7 empty] | 980.6004 | [24 empty] | 980.6004 | 0
| E3.00.03 | Level 2 | E3 | Flat | 1 | 2 | 59 | 635.076 | S/O |  | 635.076 | [30 empty] | 635.076 | 0
| E3.00.04 | Level 2 | E3 | Flat | 3 | 4 | 91.1 | 980.6004 | S/O | [7 empty] | 980.6004 | [24 empty] | 980.6004 | 0
| E3.00.05 | Level 3 | E3 | Flat | 1 | 2 | 59 | 635.076 | S/O |  | 635.076 | [30 empty] | 635.076 | 0
| E3.00.06 | Level 3 | E3 | Flat | 3 | 4 | 91.1 | 980.6004 | S/O | [7 empty] | 980.6004 | [24 empty] | 980.6004 | 0
| E3.00.07 | Level 4 | E3 | Flat | 1 | 2 | 59 | 635.076 | S/O |  | 635.076 | [30 empty] | 635.076 | 0
| E3.00.08 | Level 4 | E3 | Flat | 3 | 4 | 91.1 | 980.6004 | S/O | [7 empty] | 980.6004 | [24 empty] | 980.6004 | 0
[5 empty] | 738 | 1207 | 30185.74 | 324919.3054 |  | 13515.6013 | 75263.072 | 0 | 0 | 83007.9853 | 27355.6296 | 0 | 19792.8432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35471.6856 | 0 | 0 | 26785.1376 | 0 | 0 | 0 | 43727.3507 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 33 | 135 | 0 | 0 | 110 | 30 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 0 | 36 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 409.5637 | 557.5042 | 0 | 0 | 754.618 | 911.8543 | 0 | 899.6747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 572.124 | 0 | 0 | 744.0316 | 0 | 0 | 0 | 1066.5207 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Shared Ownership | [7 empty] | Mix | [34 empty] | S/O | 70.36%
| Number |  | Type |  |  | Area (sq.ft) |  | Total Area (Sq.ft) | [35 empty] | Rented | 29.64%
| 33 |  | Studios |  |  | 409.5637 |  | 13515.6013 | 10%
| 135 |  | 1 Bed Flats |  |  | 557.5042 |  | 75263.072 | 40.91% | [34 empty] | 3B's in Rented | 65.08%
| 110 |  | 2 Bed Flats |  |  | 754.618 |  | 83007.9853 | 42.42%
| 30 |  | 2 Bed Duplexes |  |  | 911.8543 |  | 27355.6296
| 22 |  | 3 Bed Flats |  |  | 899.6747 |  | 19792.8432 | 6.667%
| 0 |  | 3 Bed Duplexes |  |  | 0 |  | 0
| 330 | [6 empty] | 218935.1315 | 100%
Rented
| 0 |  | Studios |  |  | 0 |  | 0 | 0%
| 62 |  | 1 Bed Flats |  |  | 572.124 |  | 35471.6856 | 44.6%
| 36 |  | 2 Bed Flats |  |  | 744.0316 |  | 26785.1376 | 25.9%
| 0 |  | 2 Bed Duplexes |  |  | 0 |  | 0
| 0 |  | 3 Bed Flats |  |  | 0 |  | 0 | 29.5%
| 41 |  | 3 Bed Duplexes |  |  | 1066.5207 |  | 43727.3507
| 139 | [6 empty] | 105984.1739 | 100%
Total Residential
| 33 |  | Studios |  |  | 409.5637 |  | 13515.6013 | 7.036%
| 197 |  | 1 Bed Flats |  |  | 562.1054 |  | 110734.7576 | 42%
| 146 |  | 2 Bed Flats |  |  | 752.0077 |  | 109793.1229 | 37.53%
| 30 |  | 2 Bed Duplexes |  |  | 911.8543 |  | 27355.6296
| 22 |  | 3 Bed Flats |  |  | 899.6747 |  | 19792.8432 | 13.43%
| 41 |  | 3 Bed Duplexes |  |  | 1066.5207 |  | 43727.3507
| 469 |  |  | Total Residential |  |  |  | 324919.3054 | 100%