## Canteen
Canteen Asbestos removal and renewal of sheets
Nestle Avenue, Hayes Village
|  | week commencing | 2020-12-07 | 2020-12-14 | 2020-12-21 | 2020-01-04 | 2020-01-11 | 2020-01-18 | 2020-01-25 | 2020-02-01 | 2020-02-08 | 2020-02-15
Site set up | 1 day
Erect Scaffolding | 2 weeks
Erect netting | 2 days
Erect propping | 2 days
Close inspection and report | 1 day
Strip Asbestos sheets dispose off site | 2 weeks
Works to guttering East | 1 week
Installation of sheeting East | 1.5 weeks
Flashing to rooflights East | 3 days
Repair work to guttering West | 1 week
Works to guttering West | 1.5 weeks
Flashing to rooflights West | 3 days
Completion Inspection | 1 day
Remove netting | 2 days
Remove propping | 2 days
Remove scaffolding | 2 weeks
We have estimated 10 weeks duration
Start date is to be discussed
Above are estimates and weather depending
Asbestos must be removed before works commence to ensure complete clean down
Canteen must be empty in order for us to start works
Above assumes we are installing the scaffolding, however other contractors may have different programme lenghts that might affect the above.
Please note:- 1 week has been removed for christmas shutdown.