## Slide 1
Construction Programme – CL 001 |  |  |  |  |  |  |  |  | 
Activity Description | 2024 |  |  |  |  |  | 2025 | 2025 | 
 | Nov- Dec | Jan-Feb | Mar-Apr | May-Jun | Jul-Aug | Sep-Oct | Nov-Dec | Jan-Feb | Mar-Apr
BDL Appointed |  |  |  |  |  |  |  |  | 
Clearance of PC Planning Reserve Matters |  |  |  |  |  |  |  |  | 
RIBA Stage 4 Design |  |  |  |  |  |  |  |  | 
Demolition Inc S81 |  |  |  |  |  |  |  |  | 
Overall Construction |  |  |  |  |  |  |  |  | 
Site Establishment |  |  |  |  |  |  |  |  | 
Access Road and Parking Bays Inc MUGA Stage 1 |  |  |  |  |  |  |  |  | 
Substructures |  |  |  |  |  |  |  |  | 
Superstructures/Envelope/ Roofs |  |  |  |  |  |  |  |  | 
Internal Fit out |  |  |  |  |  |  |  |  | 
Block One –Education Facility |  |  |  |  |  |  |  |  | 
Block Two – 3 Units |  |  |  |  |  |  |  |  | 
Block Three – 3 Units |  |  |  |  |  |  |  |  | 
Block Specific Externals |  |  |  |  |  |  |  |  | 
Main External Works |  |  |  |  |  |  |  |  | 
Inspections & Lock Ups Available |  |  |  |  |  |  |  |  | 
Project Completion |  |  |  |  |  |  |  |  | 
High Level Programme
Net Construction Programme 52 Calendar weeks
PC 31/03/25
Critical Path
04/12/24

## Slide 2
Key
Offices
Storage Container/zone
Solid 2.4m Hoarding
Welfare & Office Zone (Safe Zone)
Access Gate
Main Site Delivery Route
Pedestrian Gates
Close Board Fencing
Delivery Zone
High Level Logistics
Delivery Route Main Site
Traffic Marshall
Temporary Oasis Unit for Demo and Site Establishment
Appendix B – On site Logistics Including Material Storage

## Slide 3
Enabling works and Access Roads Stage 1 Sequence: Week 01 – Week 10
 | Site Set up and Roads |  |  |  |  |  |  | 
Key | Activity | April - June 2024 |  |  |  |  |  | 
 |  | 1-2 | 3-4 | 5-6 | 7-8 | 9-10 | 11-12 | 13-14
1 | Temp Site Set Up |  |  |  |  |  |  | 
2 | Tree Crown Lift |  |  |  |  |  |  | 
3 | Storm Sewer Connection |  |  |  |  |  |  | 
4 | Boundary Fencing |  |  |  |  |  |  | 
5 | Site Access Roads & Parking Bays |  |  |  |  |  |  | 
6 | Muga Stage 1 (for Storage and Turning) |  |  |  |  |  |  | 
7 | Full Set Up |  |  |  |  |  |  | 
Notes
Demo Completes in week -1
Temp Oasis Unit in Place for Week 1 – 8 whilst parking Bays Construction
Pollarding to trees under approval from LBH
Hoarding to front in place Week 1
Replacement of boundary fencing from Week 2 onwards to remainder of site
MUGA completes in two stages to enable on- site logistics and turning circle
SW Connection undertaken in two Halves to keep Charville Lane Operational
1
2
3
4
5
6
7
8
8. Site parking weeks 1-8

## Slide 4
Substructures and Superstructures Sequence: Week 11 - Week 32
 | Substructures and Superstructures |  |  |  |  |  |  | 
Key | Activity | July – November 2024 |  |  |  |  |  | 
 |  | 11-13 | 14-16 | 17-20 | 21-23 | 24-26 | 27-29 | 30-32
A | Substructures |  |  |  |  |  |  | 
B | Brickwork & Scaffold |  |  |  |  |  |  | 
C | Roof construction and Covering |  |  |  |  |  |  | 
D | Scaffold Strike and Windows |  |  |  |  |  |  | 
E | Internals Commence |  |  |  |  |  |  | 
Notes
Blocks Numbered 1,2 and 3 as shown – This is also the general sequence of Build
Blocks are served by 1 no loading bay per block which rises with Scaffold
No Access Required around the back of Blocks 1 and 2
Blocks 1 and 2 have a linked scaffold from 1st Lift
MUGA used as part of logistics route
2
1
3
Top Out Wk 26
Forklift Routes
Site parking week 9 - 32

## Slide 5
Internals and External Works Sequence:
Week 33 – Week 48
Internal and External Works |  |  |  |  |  |  |  | 
Activity | December - March 2024 |  |  |  |  |  |  | 
 | 33-34 | 35-36 | 37-38 | 39-40 | 41-42 | 43-44 | 45-46 | 47-48
Internals |  |  |  |  |  |  |  | 
Externals Works |  |  |  |  |  |  |  | 
Muga Part 2 |  |  |  |  |  |  |  | 
Inspections |  |  |  |  |  |  |  | 
Decant Site Offices |  |  |  |  |  |  |  | 
Project Completion |  |  |  |  |  |  |  | 
Notes
Blocks Numbered 1,2 and 3 as shown – This is also the general sequence of Internals
Externals Works released by Scaffold down dates
MUGA Part 2 generated from Block Specific External Works
Inspections on a block by block basis
2
1
3
Site parking week 33 - 48

## Slide 6
16/10/2023
Assumed Planning Consent
09/02/15
2024
2024
04/12/2023
Execute Contracts
08/04/2024
Start on Site Construction
02/02/2024
Demolition Complete
12/06/2024
Roads Complete Site Established
Roads
12/06/2024
Substructures Commence
17/07/2024
Superstructures Commence
02/08/2024
Substructures Complete
25/09/2024
Internals Start
Fit Out /Testing and Commissioning/Inspections
17/10/2024
Watertight All Units
External Works Commence
24/10/2024
Superstructures complete
29/01/2025
Inspections Commence
28/02/2025
All Units Inspected
07/03/2025
External Works Complete
31/03/2025
Project Completion
Substructures
Superstructures
Superstructures
2023
14/11/2024
2025
Externals Works and MUGA
All Units Locked Up

## Slide 7
Primary Route to Site Via M25 and A40
Secondary Route to Site Via M25 and A40
Site Access Via A4020 & Pole Hill Road
Appendix A – HGV Construction Vehicle Routing