## Zone 2
ZONE 2 ANNUAL GROUNDS MAINTENANCE PROGRAME
| Key: |  | Z | Planned Task | [6 empty] | Complete Task | [5 empty] | X | Task not completed
TASK / AREA | 2023 | [25 empty] | 2024
| July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June
WEEK NUMBER | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
Litter Picking | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 31 | 8 | 15 | 21 | 29 | 6 | 13 | 20 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 2 | 8 | z | z | z | z | z | z | z | z | z | z | z | z | z | z | z | z | z | z | z | z | z | z | z | z
Waterbody Maintenace Visit | July 31: X; August 32: 12; August 36: 30; September 39: 29; October 44: 30; November 48: 30; December 52: 22; January 5: z; February 9: z; March 14: z; April 18: z; May 22: z; June 27: z
Bus Shelter Cleaning | July 31: 31; August 36: 31; September 39: 29; October 44: 31; November 48: 30; December 52: 25; January 5: z; February 9: z; March 14: z; April 18: z; May 22: z; June 27: z
Green Waste Processing | January 3: 11
LAWNS
Mowing & Strimming 35 - 50mm | 3 | 10 | 18 | 26 | 3 | 8 | 15 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 |  | 13 |  | 20 |  | 18 |  |  |  | z |  | z |  | z | z | z |  | z |  | z |  | z |  | z | z | z | z | z | z | Z | Z | Z | Z | Z
Mowing Grass Banks | July 28: 3; July 29: 10; July 30: 19; July 31: 27; August 32: 4; August 34: 15; August 36: 28; September 37: 11; September 39: 25; October 41: 9; October 43: 23; November 46: 13; November 48: 20; March 10: z; March 13: z; April 15: z; April 17: z; April 18: z; May 19: z; May 20: z; May 21: z; May 22: z; June 23: Z; June 24: Z; June 25: Z; June 26: Z; June 27: Z
Edging | July 31: 28; August 36: 24; September 39: 20; October 44: 17; November 48: 24; December 51: 18; January 5: z; February 9: z; March 14: z; April 18: z; May 22: z; June 27: z
Fertilising Spring / Summer Delta 12-4-8 + 0.5% Fe + Trace Elements 50 bags | July 28: 12; August 35: 17; March 13: z; May 20: z
Fertilising Autumn / Fineturf 5-5-10 + 4%Fe 50 bags | November 47: 22; January 5: z
Soil PH Treatment | July 28: 12; November 47: 22; January 3: z; May 20: z
Weeding (Selective Spray) | bar: March 10; April 17; June 23
Scarification | August 32: 9; October 42: 16; October 43: 17; April 17: z; April 18: z
Aeration Tine with machine | August 32: 9; October 42: 16; October 43: 17; February 6: z; May 19: z
Top Dressing & Overseed Patches | October 40: 10; April 16: z
HEDGE TRIMMING
Hornbeam / Carpinus | July 28: 7; July 29: 14; July 30: 20; July 31: 28; August 32: 4; June 23: z; June 25: z; June 27: z
Abelia | July 31: 27; August 32: 3
Pyracantha | August 33: 6
Lonicera | August 34: 7; September 39: 18; April 18: z; June 25: z
Lavender | August 35: 8; October 44: 20; December 50: 14; December 51: 15
Cotoneaster | July 28: 6; August 36: 18; May 19: z
Laurel IncOtto & Portugese | July 28: 7; August 36: 21; November 45: 5; November 46: 6; May 21: z
Yew / Taxus | August 34: 15; September 36: 12; November 46: 20; May 20: z
Eleagnus | September 38: 20
Viburnum Tinus | July 30: 21; September 38: 27; September 39: 30; May 19: z
Viburnum Opolus / Lanata | July 30: 12; September 39: 30; May 19: z
Juniper | July 30: 13; September 39: 29
Ivy on Wall | July 30: 16; October 40: 6; May 20: z
Thuja | bar: May 21
Forsythia | September 38: 20; May 22: z
HARD STANDING
Ivy Over Kerbs | September 38: 21; January 2: z; March 14: z; June 27: z
Spraying Hard Surfaces | July 28: 7; July 30: 14; August 32: 4; August 34: 9; September 37: 15; September 39: 29; October 42: 20; February 6: z; February 8: z; March 11: z; March 14: z; April 16: z; April 18: z; May 20: z; May 22: z; June 24: z; June 26: z
Road Sweeper | July 30: 12; August 34: 16; September 37: 13; October 42: 18; November 46: 15; December 51: 13; January 3: z; February 8: z; March 13: z; April 16: z; May 20: z; June 25: z
Sweep Kerbs | July 28: 7; July 30: 27; August 32: 6; August 34: 15; August 36: 25; September 37: 15; September 39: 29; October 41: 13; October 43: 27; November 45: 6; November 47: 17; December 49: 8; December 51: 18; January 1: z; January 3: z; January 5: z; February 7: z; February 9: z; March 11: z; March 14: z; April 16: z; April 18: z; May 20: z; May 22: z; June 24: z; June 26: z
SHRUB BORDERS
Weed Shrub Borders | July 28: 6; July 30: 11; August 32: 10; August 34: 14; August 36: 29; September 37: 14; September 39: 25; October 41: 12; October 43: 24; November 45: 8; November 47: 21; December 49: 6; December 51: 20; January 1: z; January 3: z; January 5: z; February 7: z; February 9: z; March 11: z; March 14: z; April 16: z; April 18: z; May 20: z; May 22: z; June 24: z; June 26: z
Pruning Deadheading Perennial Plants | July 29: 12; August 33: 11; September 38: 12; October 42: 17; November 46: 16; March 13: z; April 17: z; May 21: z; June 25: z
Shrub feed | bar: March 10; May 19
Mulch Top Up | December 49: 4; December 50: 5; January 3: z; February 7: z
TREES
Annual Lime Pollarding | September 36: 8; September 37: 15; September 38: 22; September 39: 29
Check / Raise Low Branches | July 31: 31; September 39: 29; October 44: 27; November 48: 24; December 52: 21; January 5: z; February 9: z; March 14: z; April 18: z; May 22: z; June 26: z
Tree Circles - Weed & Edge | July 29: 19; July 31: 25; August 33: 17; September 37: 15; September 38: 18; October 42: 18; October 43: 19; October 44: 20; November 48: 20; December 50: 14; December 52: 20; January 2: z; January 4: z; February 6: z; February 8: z; March 10: z; March 13: z; April 15: z; April 17: z; May 19: z; May 21: z; June 25: z; June 27: z
Irrigation Start Up and Drain Down | November 46: 7; April 16: z
PLANTERS
Feeding - Liquid Fertilizer | July 29: 14; July 31: 28; August 34: 10; September 39: 22; January 5: z; February 9: z; March 14: z; April 18: z; May 22: z; June 27: z
Watering | July 28: x; July 29: 14; July 30: x; July 31: x; August 32: x; August 33: 11; August 34: 14; August 35: x; August 36: x; September 36: x; September 37: x; May 19: z; May 21: z; June 23: z; June 25: z; June 27: z
LEAF CLEARANCE
Lawns | September 39: 29; October 40: 6; October 41: 13; October 42: 20; October 43: 27; October 44: 31; November 45: 3; November 46: 10; November 47: 17; November 48: 24; December 50: 8; December 51: 15; January 1: z
Beds & Borders | October 41: 11; October 43: 25; November 45: 8; November 47: 15; December 49: 6; December 50: 13; December 51: 19; January 2: z
Hard Standing Areas | [13 empty] | 6 | 13 | 20 | 27 | 31 | 3 | 10 | 17 | 24 |  |  | 19 |  | z
Note on G7: Bogdan Balut: MOVED DUE TO COVID
Note on AW28: Bogdan Balut: Not required
Note on D54: Bogdan Balut: not required rain
Note on F54: Bogdan Balut: not required rain
Note on G54: Bogdan Balut: not required rain
Note on H54: Bogdan Balut: not required rain