## Sheet1
SuDS Outstanding Comments - Response
Condition 17 - Original
LBH Comment | Ark Return Comment
Infiltration trenches were not included within drainage drawings | The capacity of the infiltration trenches in question have been incorporated in the overall SuDS capacity of the site. The calculation's are in line with requirements of "Drainage Statement Condition 16".
Photos of filtration trenches | As above, filtration trenches haven't been incoprated within the final site drainage design.
Photos of full extent of permeable paving | See attached additional phtographs of finished permeable paving and roadwork "SuDS Block Paving Photographs"
Confirmation statement signed by chartered engineer | Signed letter for Block 2 and Block 3 attached.
Condition 15 - Slot-In
LBH Comment | Ark Return Comment
As built showing two attenuation tanks (6 and 8) | The capacity of the attenuation tanks 6 and 8 have been incorporated in the overall SuDS capacity of the site. The calculation's are in line with requirements of "Drainage Statement Condition 14".
As built showing rainwater harvesting tank. | The capacity of the rainwater harvesting tank located in the Slot-In area of site has been incorporated in other rainwater harvesting tanks located throughout site. The calculation's are in line with requirements of "Drainage Statement Condition 14".
As built showing basin. | The basin is now subject to a separate planning permission for Block 4 of this campus and will be constructed within Block 4.
Photos showing two attenuation tanks (6 and 8) | No attenuation tanks in slot-in demise, as noted above.
Photos showing rainwater harvesting tank. | No rainwater harvesting tanks in slot-in demise, as noted above.
Photos showing basin. | No basin in Block 2 and Block 3 demise, as noted above.
Confirmation statement signed by chartered engineer | Signed letter for Block 2 and Block 3 attached.